## Scope Assumptions
Scope Assumptions — written so they can be disproved (two of them will be, in Phase 02)
Preliminary position: 604 systems believed in scope. This is a hypothesis, not a conclusion. Phase 02 tests it.
ID | Assumption | Basis | What would disprove it | Consequence if wrong
A-01 | The Verition P2PE solution is deployed as validated at all 482 stores and all 1,914 lanes, and is operated in accordance with the P2PE Instruction Manual | Solution is listed by the Council; deployment was managed centrally | A lane running a non-listed device or firmware; a POI connected outside the approved network path; a PIM control not performed | The P2PE scope reduction fails for the affected stores; those store environments become CDE
A-02 | No account data is captured anywhere in the store lane except inside the POI device | No manual-entry path exists in the POS application; no imprinters in use | A keyed-entry path to a non-POI device; card numbers written on paper at the lane; a receipt printing more than the permitted digits | Store systems re-enter the CDE; Requirement 3 obligations attach to the store estate
A-03 | On all six payment templates, card fields are rendered exclusively inside the Truvance-served iframe, and no Marketa origin collects a card field | Integration design; developer attestation | A template collecting a card field on a Marketa origin; a fallback form; a "manual entry" path for customer service | The AWS e-commerce tier becomes CDE — the single largest possible scope expansion in the programme
A-04 | No account data exists in the call-recording estate, because DTMF suppression prevents spoken and keyed PAN from being recorded | Cadence masking is deployed and in daily use | A recording containing an audible or transcribed card number | The recording archive becomes an account-data store; Requirement 3, 9 and 12.10.7 obligations attach; a risk is raised, not lowered
A-05 | Marketa stores only Truvance-issued tokens and truncated PAN; no full PAN exists at rest anywhere in the estate, including email and collaboration platforms | Architecture intent; tokenisation deployed across all three channels | A single instance of full PAN at rest, anywhere, in any format | The holding location enters the CDE and 12.10.7 procedures are invoked; the programme's central claim requires qualification
A-06 | Sensitive authentication data — CVV2, full track, PIN and PIN block — is never stored after authorisation | Requirement 3.3.1 prohibition; no business process requires it | Any SAD found post-authorisation, in any system, log or archive | The most serious finding available to a merchant; immediate escalation under §7 of 01.06
A-07 | Dispute, chargeback and refund processes operate solely on tokens and truncated PAN; no document held for those processes bears a full card number | Payment operations process documentation | Scanned correspondence, issuer packets or exported files containing full PAN | A previously invisible data store enters the CDE; the "payment operations is 8 systems" position needs restating
A-08 | The 1,238 systems outside the believed-in-scope set have no account data, no connectivity to the CDE, and no ability to affect its security — including systems recorded as decommissioned | CMDB tagging; network design intent | Discovery finding account data on any of them; a network path proving connectivity; a "decommissioned" host still powered and reachable | The system enters scope, and the reliability of the CMDB as a scoping input is itself called into question
A-09 | Store back-office networks are segmented from the corporate CDE, and store guest wireless is segmented from store back-office | Network design and configuration standards | A penetration test proving a reachable path between zones | Segmentation cannot be relied on for scope reduction until remediated and re-tested; every system on the reachable side is in scope in the interim
A-10 | Marketa cannot reverse a Truvance token to a PAN by any means available to it | Contractual position; no key material held | Any Marketa-side capability, API entitlement or cached mapping that permits detokenisation | Tokens become cardholder data in Marketa's hands, and every system storing them enters scope
A-11 | Truvance, Cadence and Verition maintain valid PCI validation, and Verition's P2PE solution remains listed, throughout the compliance year | Current AOCs and listings held on file | A lapsed AOC, a delisted solution, or a validation covering a different service than the one consumed | The relevant scope reduction is unsupported until re-established; Cardinal is notified under obligation C7
A-12 | Payment acceptance occurs only through the three channels documented in 01.01 — no other business unit, campaign or partner accepts cards on Marketa's behalf | Payment operations owns all merchant IDs | An unrecorded merchant ID, a departmental payment page, an event or pop-up acceptance path | An entire undocumented acceptance channel enters scope, with no controls and no evidence history

## Constraints
Programme Constraints — fixed properties the plan must be built around
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 01 · Illustrative Portfolio Sample
ID | Constraint | Description | Effect on scope work and delivery
CON-01 | Seasonal change freeze, October to January | No change to store systems, store networks or the POS estate during peak trading. Enforced by Store Operations and Merchandising, not by IT, and not waivable by the programme | All store-side change must complete by 2026-09-30. It is the reason control implementation runs April to July, why the application penetration test is in September, and why QSA fieldwork is in early November — an assessment observes, it does not change
CON-02 | 482 stores means every store-side change is a 482× rollout | A change that takes ten minutes per store is 80 hours of field effort before travel, scheduling, verification or failure handling. A change requiring an on-site visit is a multi-week programme in its own right | Favours centrally deployable and observation-based controls. Directly shapes the design of the 9.5.1 inspection regime, which had to be executable by store colleagues on shift rather than by visiting engineers
CON-03 | Vendor-locked POS back-office appliances | A subset of store back-office appliances is supplied and maintained by the vendor under terms that prevent Marketa installing agents or holding privileged credentials | Prevents authenticated internal scanning under 11.3.1.2 on the affected components without vendor cooperation. This is a known constraint at programme start, not a surprise discovered later, and it is carried as a delivery risk from day one
CON-04 | The QSA fieldwork window is fixed | Sable Ridge Assurance is on site 2026-11-02 to 2026-11-20. The window was reserved at engagement and cannot be moved late in the year without losing it | Everything is planned backwards from this date. Controls must be operating long enough before it to produce a meaningful sample — see 01.12
CON-05 | Cardinal's 31 December filing deadline | Obligation C3. The AOC is due on or before 31 December each year | Leaves roughly six weeks between the end of fieldwork and the deadline for report production, review and signature — with no room for a second attempt
CON-06 | Budget of $4,600,000 | Approved envelope across FY2026 and FY2027, with 4% contingency. Variance above 10% of a phase budget requires the CFO | Scope reduction is the primary cost control. Every system that stays in scope carries recurring cost in tooling, scanning, evidence and assessor time — which is why the discovery spend is treated as an investment rather than an overhead
CON-07 | 11.4 FTE-equivalents, drawn from teams with day jobs | Store operations, e-commerce engineering and infrastructure are all contributing part-time capacity alongside trading-critical work | Sequencing matters more than effort. Two workstreams competing for Trevor Kim's network engineers cannot both be on the critical path
CON-08 | No pre-existing external attestation to draw on | Marketa holds no SOC 2, ISO 27001 or equivalent report of its own. It is privately held, is not an SEC registrant, and has no SOX control population to reuse | Every piece of control evidence in the assessment must be produced by this programme from a standing start
CON-09 | Seasonal workforce of up to 6,800, October to January | Temporary colleagues join precisely during the freeze and precisely when transaction volume peaks | Awareness training under 12.6.3 and POI inspection under 9.5.1 must both work for people who joined six weeks ago. The charter's 95% completion bar exists because of this constraint

## Stakeholders
Stakeholder Register — internal
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 01 · Illustrative Portfolio Sample
ID | Stakeholder | Who | Posture | Interest | What they need | What the programme needs
S-01 | Board — Audit Committee | Priya Raghunathan | Manage closely | Assurance that a $4.2B retailer's payment exposure is governed | Honest, unfiltered reporting; early warning of any threat to validation | Oversight, challenge, and air cover when an honest finding is unwelcome
S-02 | Executive leadership | Diane Okafor, Raymond Voss, Curtis Lang | Manage closely | Continuity of card acceptance; predictable cost; the acquirer relationship | A credible plan, a stable forecast, no surprises | Funding, mandate, and visible sponsorship at the point where a business unit says no
S-03 | Payment Operations | Elena Marchetti | Manage closely | Settlement, chargebacks and refunds keep working | Controls that do not break daily operations; realistic evidence demands | Business ownership of the CDE; process walkthroughs; the truth about what the team actually does
S-04 | Infrastructure &amp; Network | Trevor Kim | Manage closely | A network they can operate and troubleshoot | Clear scope so segmentation is designed once; protected engineering capacity | Segmentation design and build; MFA; configuration standards; 9 zones delivered by mid-year
S-05 | E-commerce Engineering | Sonia Rendell | Manage closely | Release velocity; conversion rate; site stability | Requirements expressed as engineering constraints, not policy prose | 6.4.3 script inventory; 11.6.1 monitoring; control over what executes on payment pages
S-06 | Marketing Technology | Function within Merchandising and Digital | Keep satisfied | Measurement, personalisation and attribution on the highest-value pages on the site | Advance notice; a workable path to get a legitimate tag approved | Acceptance that payment-page tags become a governed change, not a self-service action
S-07 | Security Operations | Marcus Hale | Manage closely | Signal over noise; tooling that works | Funding for automated log review; scope stability so coverage can be finished | Logging across 71 components; ASV and internal scanning; FIM; incident detection
S-08 | Store Operations | Adaeze Nwosu | Manage closely | Selling. Every minute of colleague time is a trading decision | The smallest possible ask, expressed in store language, deliverable on shift | Quarterly inspection of 1,914 terminals; device inventory accuracy; tamper reporting
S-09 | Regional and store managers | Via Adaeze Nwosu, monthly readiness call | Keep informed | Payroll hours; task load; audit outcomes for their region | Tools, training and a task that fits into an existing routine | Actual execution of the inspection cycle in 482 stores
S-10 | Call Centre | Bill Traynor | Manage closely | Average handle time; conversion; customer experience | Recognition that the secure payment session costs seconds per call | Zero-tolerance enforcement of the secure payment session; bypass detection
S-11 | Call centre agents | Via Bill Traynor | Keep informed | Getting through the call; hitting targets | Clear rules and a script for the awkward customer moment | Never accepting a spoken card number, even when the customer offers
S-12 | Internal Audit | Rosa Delgado | Keep satisfied | Independent assurance to the Audit Committee | Unfiltered access to evidence and people | An independent October review, timed so its findings can be acted on
S-13 | Legal | Frank Mueller | Keep satisfied | Contractual exposure; provider agreements | Early sight of TPSP agreements and any non-compliant filing decision | 12.8.2 security schedules; advice on statutory obligations, which are separate from PCI DSS
S-14 | Human Resources | HR operations, via Owen Castellanos | Keep informed | Onboarding throughput, especially the seasonal intake | Training that can be delivered inside existing onboarding | 12.6.3 delivery to ~34,000 colleagues plus 6,800 seasonal; 12.7.1 screening records
S-15 | Finance and Procurement | Via Raymond Voss | Keep informed | Spend against the $4.6M envelope; contract terms | Predictable phasing; early notice of variance | Purchase-order velocity that does not delay tooling; PCI schedules in new contracts
S-16 | Distribution centre operations | Via Curtis Lang | Monitor | Throughput; no new IT friction | Confirmation that DC systems are largely out of scope, once proven | Cooperation with discovery scanning and removable-media controls under 5.3.3
S-17 | All colleagues | Via HR and the awareness programme | Keep informed | Not being blamed for something they were never told | Training that is short, concrete and relevant to their job | Report PAN found where it should not be, under 12.10.7; never write a card number down