## Evidence Classes
Evidence Indexed During Fieldwork
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Evidence class | Count | What it can prove | What it cannot prove
Documentation items examined | 1284 | That a control is defined, approved and has a record | That anybody followed it
System configuration examinations | 228 | The state of a component at the moment it was read | That the state held for the period
Interviews | 47 | That the person operating a control understands it | That the control operated. 47 interviews across 39 distinct individuals
Process observations | 61 | That the process runs the way it is written | That it runs that way when nobody is watching
Independent assessor testing actions | 34 | What the assessor could and could not do, directly | Anything about the population the test was not run against
Total indexed evidence artefacts | 1654 | The report's evidentiary base, referenced throughout Part II | Retained by Sable Ridge and by Marketa for three years

## Assessor Requests
The Evidence Request Log — the Payoff for Seven Phases
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Line | Count | Share | Note
Evidence requests raised across the engagement | 214 | 100% | Raised by Sable Ridge from the pre-fieldwork plan onward
Satisfied from artefacts that already existed | 186 | 86.9% | Produced during the work rather than for the assessment. This number is the phase's measurable payoff
Required new production | 28 | 13.1% | Point-in-time observations nobody can pre-produce — live configuration reads, a witnessed restore, a witnessed POI inspection
Re-requested after a first response was judged insufficient | 6 | 2.8% | A subset of the 214, not an addition to it
Unsatisfied | 0 | 0% | No request went unanswered
Register entry this moves | R-42 | Low 6 → Low 3 | Evidence produced during the year is not retained in a form the assessor can sample in November

## Fieldwork Schedule
On-Site Fieldwork — 2026-11-02 to 2026-11-20
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Week | Dates | Location | Requirements | Team
Week 1 | 2026-11-02 → 11-06 | Columbus HQ and Columbus data centre | 1, 2, 3, 4 and the Requirement 12 documentation set | Grant Whitfield, Amara Osei
Week 2 | 2026-11-09 → 11-13 | Austin technology office, call centre, Ashburn co-location (11-12) | 6, 7, 8, 10, 11 | Grant Whitfield, Amara Osei
Week 3 | 2026-11-16 → 11-20 | Store estate — 28 stores over three days; closing meeting 11-20 | 5, 9 | Grant Whitfield, Amara Osei and two supporting assessors

## In-Flight and Observations
Corrected During Fieldwork, and Observed Without Effect
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Category | Count | Treatment | Governing decision
Items corrected during fieldwork | 9 | Recorded in the ROC as corrected during the assessment. A requirement corrected during fieldwork may be assessed In Place; one corrected after the ROC may not | ADR-0029
Assessor observations not affecting a disposition | 17 | Recorded and inherited by Phase 09. An observation is not a finding, and treating it as one is how observations stop being raised | —
Determinations where the assessor's initial position differed | 4 | Two resolved in Marketa's favour (3.5.1.3, 10.4.2), two did not (5.3.3, 1.2.8) | —
Requirements assessed Not Tested | 0 | None. Every applicable sub-requirement was tested | ADR-0004