## Risk Movement
Phase 08 Risk Movement — Every Movement Is a Likelihood Movement
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Risk | From band | From L | From I | From score | To band | To L | To I | To score | Band changed? | Basis
R-17 — embedded credentials in legacy batch integrations | High | 4 | 4 | 16 | Moderate | 2 | 4 | 8 | YES | CAP-07 complete 2027-01-29 and re-tested 2027-02-18. Both credentials removed from the shell wrapper and the properties file and moved to CT-14 run-time retrieval; source files and the wider repository re-scanned; 8.6.2 In Place. The exit criterion was published in Phase 05 and met
R-36 — internal scanning not authenticated on 9 components | High | 4 | 4 | 16 | Moderate | 2 | 4 | 8 | YES | CAP-06 complete 2027-01-30 and re-tested 2027-02-18. Contract amendment executed 2027-01-08, credentials released 2027-01-19, first authenticated scan of all nine 2027-01-27, clean confirmatory scan 2027-01-30; 11.3.1.2 In Place. The residual changed shape: the exposure is now contractual, not technical
R-13 — seasonal workforce access | Moderate | 4 | 3 | 12 | Moderate | 3 | 3 | 9 | no | The 6,800-person 2026 intake provisioned and deprovisioned under the new joiner-mover-leaver process, through a full October–January peak, with 0 orphans at the January reconciliation. The mechanism has now met the season it was built for
R-32 — a boundary-affecting change is classified as routine, receives no scope-delta review, no second approver and no re-test obligation, and quietly alters what a zone can reach | Moderate | 3 | 4 | 12 | Moderate | 2 | 4 | 8 | no | 45 change records sampled by the assessor — its own stratified selection of 12 significant and 33 standard from a population of 1,109 — with 0 exceptions, plus independent examination of all 9 network security control rulesets. The counter-evidence sits in the same cell: the 1.2.8 in-flight correction is an instance of exactly this class, found by the assessor and not by Marketa, which is why the movement is 12 → 8 and no further
R-41 — programme capacity is lost to trading-critical work and a store-side control misses the 2026-09-30 cut-off imposed by the seasonal freeze, leaving it without operating history before QSA fieldwork | Low | 3 | 2 | 6 | Low | 2 | 2 | 4 | no | The risk was written in Phase 03 as a forecast about precisely this event, and the event has now occurred. Fieldwork ran 2026-11-02 to 11-20; every store-side control had operating history; no requirement was assessed as lacking it; 214 evidence requests answered with 0 unsatisfied. It moves one step and no further because the cut-off held once, in a year with an unusual amount of executive attention on it, and the 2027 cycle faces the same freeze with less
R-42 — evidence produced during the year is not retained in a form the assessor can sample in November — screenshots without dates, reports without populations, attestations without a named attester | Low | 2 | 3 | 6 | Low | 1 | 3 | 3 | no | 186 of 214 assessor evidence requests (86.9%) satisfied from artefacts that already existed, 0 unsatisfied, and only 6 re-requested after a first response was judged insufficient. The 28 requiring new production were point-in-time observations that cannot be pre-produced
R-38 — physical access to store stockrooms and network cabinets is not controlled to the standard the network design depends on, so a person with a cable has the access the segmentation model assumes they do not | Low | 3 | 2 | 6 | Low | 2 | 2 | 4 | no | R-38's untested surface was recorded as accepted in 06.11 §5. The assessor physically examined stockrooms and network cabinets across 28 stores it selected itself, including store 0417, with no store-level finding. This is the first external examination of that surface in the programme

## Register Position
The Register Across Phase 08
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Rating | Entering Phase 08 | Exiting Phase 08 | Change | Note
High | 2 | 0 | −2 | R-17 and R-36 — the two Not in Place findings, remediated and re-tested
Moderate | 22 | 24 | +2 | Both arrivals from High. R-13 and R-32 move within the band
Low | 20 | 20 | 0 | R-41, R-42 and R-38 move within the band
TOTAL | 44 | 44 | 0 | No entry has been closed or removed in twelve months
Forecast at Phase 09 close | — | 0 High · 13 Moderate · 31 Low | — | Requires eleven Moderate entries to reach Low on operating evidence Phase 08 does not have

## CAP Milestones
Corrective Action Plans — CAP-07 and CAP-06
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Plan | Requirement | Date | Milestone | Status
CAP-07 | 8.6.2 | 2026-12-11 | Recorded in AOC Part 4 with a target date of 2027-01-31; supersedes OI-05-01 | Complete
CAP-07 | 8.6.2 | 2026-12-17 | Change-freeze exemption approved by the Steering Committee | Complete
CAP-07 | 8.6.2 | 2027-01-22 | batch-icq on CDE-05 moved to vaulted credential retrieval | Complete
CAP-07 | 8.6.2 | 2027-01-29 | gl-extract on CDE-04 moved to vaulted credential retrieval | Complete
CAP-06 | 11.3.1.2 | 2026-12-11 | Recorded in AOC Part 4 with a target date of 2027-01-31 | Complete
CAP-06 | 11.3.1.2 | 2027-01-08 | Route A — contract amendment with Verition POS Systems executed | Complete
CAP-06 | 11.3.1.2 | 2027-01-19 | Credentials released for all nine appliances | Complete
CAP-06 | 11.3.1.2 | 2027-01-27 | First authenticated internal scan of all nine completed | Complete
CAP-06 | 11.3.1.2 | 2027-01-30 | Clean confirmatory authenticated scan | Complete
CAP-06 | 11.3.1.2 | 2027 roadmap | Route B — replacement of the appliance class, retained although not needed for the finding | Open
Both | 8.6.2 · 11.3.1.2 | 2027-02-18 | Re-assessment — 16 sub-requirements re-tested; revised ROC and AOC issued | Complete

## Re-Assessment Outcome
2027-02-18 — the Revised Position
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 08 · Illustrative Portfolio Sample
Disposition | 2026-12-11 | 2027-02-18 | Change | Note
In Place | 297 | 299 | +2 | 8.6.2 and 11.3.1.2 both met and re-tested
In Place with Compensating Control | 3 | 3 | 0 | CCW-01 and CCW-02 survive — the remediation removed the finding, not the constraint
Not Applicable | 4 | 4 | 0 | Unchanged
Not Tested | 0 | 0 | 0 | Unchanged — ADR-0004
Not in Place | 2 | 0 | −2 | The two Part 4 items
TOTAL | 306 | 306 | 0 | Population unchanged
AOC status | Non-Compliant | Compliant | — | ADR-0032 — the 2026 attestation is not withdrawn. The revised attestation is additive