## Q-01 to Q-16
The 16 questions Phase 01 required Phase 02 to answer
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 02 · Illustrative Portfolio Sample
ID | Question | Answer | Evidence grade | Owner | Status
Q-01 | Where does account data exist at rest across the entire estate? | Four locations, all outside the 604, three in populations no inventory covered | E1 | Marcus Hale | Answered
Q-02 | Is any sensitive authentication data stored after authorisation? | No. None found anywhere | E1 | Marcus Hale | Answered
Q-03 | Does the PAN traverse or rest on a Marketa system in the card-present channel? | No. Zero clear-text PAN in 3,840 test transactions across every acceptance mode | E1 | Trevor Kim | Answered
Q-04 | Is the iframe served from Truvance's origin on all six templates, with no Marketa-origin card field? | Yes, on all six, across three geographies, four device profiles and both consent states | E1 | Sonia Rendell | Answered
Q-05 | Does any historical or current call recording contain account data? | Current: no. Historic: yes — approximately 11,400 recordings | E1 | Bill Traynor | Answered
Q-06 | What do dispute, chargeback and refund processes create, and what do they contain? | Today, tokenised case records. Historically, 2,187 scanned documents bearing full PAN | E1 | Elena Marchetti | Answered
Q-07 | Can Marketa detokenise, by any route, entitlement or cached artefact? | No. Contract, entitlement, structure, cached-mapping search and a failed live attempt | E1 | Elena Marchetti | Answered
Q-08 | Which systems have network reachability to the CDE, in either direction? | Inbound: six source populations, all in Z3. Outbound: nine destination patterns. Four undocumented paths found | E1 / E2 | Trevor Kim | Answered
Q-09 | Which systems can affect CDE security though they hold no account data? | 63 components across 13 functional groups | E2 | Trevor Kim | Answered
Q-10 | Is guest wireless separated from store back-office, and back-office from corporate? | By configuration, yes. By test — not at the time of the determination, and the test subsequently proved otherwise | E2 only | Trevor Kim | Answered conditionally
Q-11 | Are systems recorded as decommissioned still powered, reachable or holding data? | Yes — 6 of 137, one holding account data | E1 | Trevor Kim | Answered
Q-12 | Do backups and replicas at Ashburn contain anything production does not? | Yes — 33 objects, copies of finding PAN-02, plus 28 unencrypted legacy sets | E1 | Marcus Hale | Answered
Q-13 | Are there acceptance channels or merchant IDs outside the three documented ones? | No live ones. One dormant merchant ID found and closed | E2 | Elena Marchetti | Answered
Q-14 | Which third parties can affect account data, and does the 01.09 register match reality? | Almost. One unrecorded connection found; one responsibility matrix clarified | E2 | Owen Castellanos | Answered
Q-15 | What is the complete population of payment pages and the scripts on them? | 6 templates, 38 scripts, 11 third-party. 3 unauthorised at first inventory | E1 | Sonia Rendell | Answered
Q-16 | What is the defensible list of assessed components, and the rationale for every exclusion? | 71 components — 8 CDE, 63 connected-to. Every exclusion recorded with its reason and its condition | E1 / E2 | Naomi Bhatt | Answered

## Assumptions
Disposition of the 12 Phase 01 assumptions — two were disproved
An assumption written so it cannot be disproved is not an assumption. A-04 and A-07 did not survive contact with evidence.
ID | Assumption | Disposition | Basis
A-01 | P2PE deployed as validated at all 482 stores and 1,914 lanes, operated per the PIM | Confirmed with qualification | Three stores with a non-conforming POI network path; seven device register serial mismatches
A-02 | No account data captured in the store lane except inside the POI | Confirmed | 3,840 test transactions, every acceptance mode, zero clear-text PAN; no keyed-entry path exists in the POS application
A-03 | Card fields rendered exclusively inside the Truvance iframe on all six templates | Confirmed | HAR capture, DOM inspection, code review, server-side parameter analysis, 90-day log analysis
A-04 | No account data in the call-recording estate | DISPROVED | ~11,400 recordings containing audible PAN, 2019-03 to 2023-06
A-05 | No full PAN at rest anywhere in the estate | Restated — see §5 | Contradicted by all four findings; not an independently testable mechanism
A-06 | No SAD stored after authorisation | Confirmed with qualification | None found — but confirmed by an accident of application design, not by a control
A-07 | Dispute, chargeback and refund processes hold no full PAN | DISPROVED | 2,187 scanned documents bearing full PAN, name and expiry
A-08 | The 1,238 excluded systems hold no account data, no CDE connectivity and no security impact | Confirmed with qualification | One held account data; six "decommissioned" systems were live; ten had security impact and entered scope
A-09 | Store back-office segmented from corporate, and guest wireless from back-office | Confirmed with qualification — configuration only | E2 configuration evidence across 482 sites; no test evidence at the determination date. See §7
A-10 | Marketa cannot reverse a Truvance token by any means | Confirmed | Contract, entitlement enumeration, token structure analysis, cached-mapping search, live negative test returning HTTP 403
A-11 | Truvance, Cadence and Verition maintain valid validation throughout the year | Confirmed with qualification | All current; the Verition P2PE Attestation of Validation dated 2025-09-12 requires renewal inside the compliance year and is tracked
A-12 | Payment acceptance occurs only through the three documented channels | Confirmed with qualification | One dormant merchant ID found and closed; no live undocumented acceptance path

## Disproved
The two disproved assumptions — remediation does not repair a disproved belief
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 02 · Illustrative Portfolio Sample
ID | What was assumed | Disposition | What disproved it | Consequence
A-04 | DTMF masking had eliminated spoken PAN from the call estate | DISPROVED | Masking was implemented forward-only in 2023-06. ~11,400 pre-masking recordings contained audible PAN | R-31 RAISED to 4 × 4 = 16 (High) on 2026-02-05
A-07 | Dispute and chargeback handling does not create documents containing account data | DISPROVED | 2,187 scanned dispute documents held PAN in clear on an unencrypted share, plus 33 backup copies | Feeds the Requirement 3 and 9 workstreams; drives P-2