## Phase 09 Movements
Phase 09 Risk Movement — the Last Eight
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
Risk | From band | From L | From I | From score | To band | To L | To I | To score | Type | Basis
R-13 — seasonal workforce access | Moderate | 3 | 3 | 9 | Low | 2 | 3 | 6 | Likelihood | OI-07-03 closed 2027-02-26. All 100 stale directory records reconciled; none held an entitlement. The published reversal condition from 08.13 §3.4 did not fire
R-22 — customer-initiated account data | Moderate | 3 | 3 | 9 | Low | 2 | 3 | 6 | Likelihood | OI-07-04 closed 2027-02-27. The complete October–January peak under DLP enforcement and the store payment-link route: 4 customer-initiated instances, all quarantined at the collector, none reaching a store colleague
R-21 — phishing delivers a foothold | Moderate | 4 | 3 | 12 | Low | 2 | 3 | 6 | Likelihood | OI-06-07 closed 2027-06-18. Two full campaigns in April and June and 3 pretext-calling tests; FIDO2 on every administrative path; report rate 41%, click-through 2.1%, 0 credential submissions
R-15 — the legacy pre-shared key remnant | Moderate | 3 | 4 | 12 | Low | 1 | 4 | 4 | Likelihood | CAP-05 closed 2027-06-12. Population 214 → 0, the static WPA2-PSK decommissioned and the SSID withdrawn. The register's only non-expiring likelihood of 1 — see §3
R-23 — the DTMF suppression point moves downstream | Moderate | 2 | 5 | 10 | Low | 2 | 3 | 6 | Impact | The Cadence renewal of 2027-03-14 added pre-notification and rollback obligations for any change to the suppression point, and the daily MOTO-C2 assertion now fails closed — the channel stops accepting card payments rather than accepting them unmasked
R-08 — account data as a by-product of an unmapped process | Moderate | 3 | 4 | 12 | Low | 2 | 3 | 6 | Impact + likelihood | Process-level data mapping completed 2027-04-30 across all 61 procedures; the Phase 07 collector-side quarantine rule now applies at every inbound path, so an unmapped process produces account data into a quarantine rather than into a store
R-18 — privileged access from a general-purpose workstation | Moderate | 3 | 4 | 12 | Low | 2 | 3 | 6 | Impact + likelihood | Privileged access workstation rollout completed 2027-05-29 across all 178 in-scope administrative personnel. A compromised general-purpose workstation no longer holds a privileged session to steal — it must compromise a second, hardened device
R-32 — a boundary-affecting change classified as routine | Moderate | 2 | 4 | 8 | Low | 2 | 3 | 6 | Impact | CSC-8's daily assertion bounds a misclassified change to at most 24 hours rather than indefinitely. The consequence is bounded; the classification error is not less likely, and likelihood is held at 2 for exactly that reason

## Final Register
The Final Risk Register — All 44 Entries at Programme Close
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
ID | Risk | Base L | Base I | Base score | Base band | Final L | Final I | Final score | Final band | Last moved
R-01 | Unauthorised or malicious script executing in the consumer browser on a payment page | 4 | 5 | 20 | High | 2 | 5 | 10 | Moderate | Phases 06–08
R-02 | POI device tampering, skimmer overlay or whole-device substitution across 1,914 terminals | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | Phases 06–08
R-03 | Store network flatness — a single configuration enforcement plane across 482 sites | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-04 | Configuration drift returns faster than assurance detects it across 482 sites | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-05 | A P2PE condition fails at one or more stores, invalidating the card-present scope reduction | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | Phases 06–08
R-06 | New unstructured repositories accumulate account data faster than discovery finds them | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-07 | Account data comes to rest in a mailbox or archive in the messaging estate | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-08 | Account data created as a by-product of an unmapped business process | 3 | 4 | 12 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-09 | Third-party concentration — Truvance is checkout, gateway and token vault across all three channels | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | Phases 06–08
R-10 | A provider's validation lapses inside the compliance year | 3 | 4 | 12 | Moderate | 2 | 3 | 6 | Low | Phases 06–08
R-11 | A responsibility gap between Marketa and a provider for after-hours detection and escalation | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-12 | Insider misuse where full PAN is legitimately visible in dispute and refund handling | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-13 | Seasonal workforce access — up to 6,800 onboarded fast and offboarded slowly, inside the freeze | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-14 | Segmentation controls in the store estate are not effective — RAISED ON EVIDENCE 2026-05-18 | 4 | 4 | 16 | High | 2 | 3 | 6 | Low | Phases 06–08
R-15 | The legacy pre-shared key remnant — a static WPA2-PSK across the store appliance estate | 3 | 4 | 12 | Moderate | 1 | 4 | 4 | Low | Phase 09
R-16 | An unauthorised wireless access point installed in a store and not detected before the next scan | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-17 | Application and system accounts hold embedded credentials in legacy batch integrations | 4 | 4 | 16 | High | 2 | 4 | 8 | Moderate | Phases 06–08
R-18 | Privileged access to a management plane from a general-purpose workstation | 3 | 4 | 12 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-19 | Assets recorded as decommissioned remain powered, reachable and unscanned | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | Phases 06–08
R-20 | Destructive or extortion malware interrupts trading across the store or distribution estate | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-21 | Phishing delivers a foothold used to reach administrative services and the brokered CDE path | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-22 | Customer-initiated account data by email, web form free-text or special-order note | 3 | 3 | 9 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-23 | A telephony change moves the DTMF suppression point downstream — condition MOTO-C2 | 2 | 5 | 10 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-24 | Call recordings retained beyond the thirteen-month rule | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —
R-25 | A cloud segmentation boundary changed by a single authorised API call, with no symptom | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-26 | Cloud logging disabled, diverted, or not monitored for absence | 2 | 4 | 8 | Moderate | 1 | 4 | 4 | Low | Phases 06–08
R-27 | Administrative-services zone concentration yields multiple paths into the CDE | 3 | 5 | 15 | High | 2 | 5 | 10 | Moderate | Phases 06–08
R-28 | Automated log review fails silently behind a dashboard that still looks healthy | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-29 | An ASV scan fails and remediation plus rescan misses the 30-day window under obligation C4 | 3 | 2 | 6 | Low | 3 | 2 | 6 | Low | —
R-30 | High and critical vulnerabilities not remediated within one month across the store estate | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-31 | Historical account data persists in the call-recording estate — RAISED ON EVIDENCE 2026-02-05 | 4 | 4 | 16 | High | 2 | 3 | 6 | Low | Phases 06–08
R-32 | A boundary-affecting change classified as routine, with no scope-delta review or re-test | 3 | 4 | 12 | Moderate | 2 | 3 | 6 | Low | Phase 09
R-33 | Scope creep — a system or relationship enters the estate without a scope determination | 3 | 4 | 12 | Moderate | 3 | 4 | 12 | Moderate | —
R-34 | The payment-page script inventory drifts as tooling is added through a tag manager | 4 | 3 | 12 | Moderate | 2 | 3 | 6 | Low | Phases 06–08
R-35 | An application flaw in the storefront exposes order data, tokens or customer records | 3 | 2 | 6 | Low | 3 | 2 | 6 | Low | —
R-36 | Nine vendor-locked POS back-office appliances cannot be authenticated-scanned — CON-03 | 4 | 4 | 16 | High | 2 | 4 | 8 | Moderate | Phases 06–08
R-37 | File integrity and change-detection coverage lapses on a CDE component | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-38 | Physical access to store stockrooms and network cabinets is not controlled to the assumed standard | 3 | 2 | 6 | Low | 2 | 2 | 4 | Low | Phases 06–08
R-39 | Media containing account data disposed of without a certificate, or held past retention | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-40 | Awareness completion falls below the charter bar during seasonal onboarding | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —
R-41 | Programme capacity is lost to trading-critical work and a store-side control misses its cut-off | 3 | 2 | 6 | Low | 2 | 2 | 4 | Low | Phases 06–08
R-42 | Evidence not retained in a form the assessor can sample in November | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-43 | Incident procedures documented but not exercised against the scenarios this estate produces | 2 | 3 | 6 | Low | 2 | 3 | 6 | Low | —
R-44 | Time synchronisation drifts or a log source is lost without alerting | 2 | 2 | 4 | Low | 2 | 2 | 4 | Low | —

## Forecast vs Actual
The Close Forecast, and the Miss
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
Line | Forecast (03.12 §6) | Actual at 2027-06-30 | Variance | Explanation
High | 0 | 0 | 0 | Met. Nine High entries at baseline, none at close, and none ever accepted
Moderate | 13 | 16 | **+3** | Missed. Three entries short of the forecast
Low | 31 | 28 | **−3** | Missed by the same three
Total entries | 44 | 44 | 0 | No entry closed, removed or added in eighteen months
Forecast Moderate→Low delivered in Phase 06 | — | R-10, R-19, R-26, R-34 | 4 of 13 | Delivered
Forecast Moderate→Low delivered in Phase 09 | — | R-08, R-18, R-21, R-22, R-23, R-32 | 6 of 13 | Delivered
Forecast Moderate→Low NOT delivered | — | R-04, R-28, R-33 | 3 of 13 | All three scored 3 x 4. Under this register's discipline a 3 x 4 entry reaches 2 x 4 = 8 and stops. EIGHT IS A FLOOR
Forecast High→Low, delivered to Moderate 8 | — | R-17, R-36 | 2 | Both arrive at 2 x 4. 06.12 §7 forecast Low; 08.13 §6.3 corrected it
Not forecast to move, but reached Low | — | R-13, R-15 | +2 | Credited in the reconciliation
Net | 13 Moderate | 16 Moderate | +3 | The forecast was written in month 7 of 18, before the scoring discipline had been tested against a single year of evidence

## Impact Reductions
Every Impact Reduction in the Programme — All Seven, Named
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
# | Phase | Risk | Impact | The change in consequence that justified it
1 | 06 | R-10 — a provider's validation lapses inside the compliance year | 4 → 3 | The suspension rule recorded in advance: a lapse became a defined change in the assessed position rather than an improvised argument under deadline pressure
2 | 07 | R-14 — segmentation controls in the store estate are not effective | 4 → 3 | The path the test actually proved was Z7 to Z5 — guest wireless into a connected-to store zone — while the Z3-to-Z1 crossing into the CDE is separately enforced at an inline prevention point
3 | 07 | R-31 — historical account data in the call-recording estate | 4 → 3 | The historical corpus was destroyed and evidenced; the residual is the forward-only creation path
4 | 09 | R-23 — the DTMF suppression point moves downstream | 5 → 3 | The Cadence renewal of 2027-03-14 added pre-notification and rollback obligations, and the daily MOTO-C2 assertion now FAILS CLOSED — the channel stops accepting card payments rather than accepting them unmasked
5 | 09 | R-08 — account data as a by-product of an unmapped process | 4 → 3 | The collector-side quarantine rule now applies at every inbound path: an unmapped process produces account data into a quarantine rather than into a store
6 | 09 | R-18 — privileged access from a general-purpose workstation | 4 → 3 | The privileged access workstation rollout completed 2027-05-29: a compromised general-purpose workstation no longer holds a privileged session to steal
7 | 09 | R-32 — a boundary-affecting change classified as routine | 4 → 3 | CSC-8's daily assertion bounds a misclassified change to at most 24 hours rather than indefinitely. The consequence is bounded; the classification error is not less likely, and likelihood is held at 2 for exactly that reason