## Metric Catalogue
Continuous Compliance Metric Catalogue — 34 Measures
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
ID | Measure | Category | Leading / lagging | Owner | Frequency | Board scorecard
M-01 | Validation status filed with the acquirer | A | Lagging | Raymond Voss | Annual | Yes — BSC-01
M-02 | Applicable sub-requirements assessed Not in Place | A | Lagging | Owen Castellanos | Annual | Yes — BSC-02
M-03 | Compensating controls in force, and how many carry a vendor remediation roadmap | A | Lagging | Naomi Bhatt | Annual | Yes — BSC-11
M-04 | Customized-approach assessor hours consumed against estimate | A | Lagging | Owen Castellanos | Annual | No
M-05 | Evidence requests satisfied from artefacts that already existed | A | Lagging | Owen Castellanos | Annual | No
M-06 | Assessed system components against the confirmed 12.5.2 scope | B | Lagging | Owen Castellanos | Monthly | No
M-07 | 12.5.1 component-register reconciliation exceptions | B | Leading | Owen Castellanos | Monthly | No
M-08 | Payment-page scripts inventoried, authorised and integrity-assured | B | Lagging | Sonia Rendell | Monthly | Yes — BSC-06
M-09 | Unexpected PAN locations found per full discovery run | B | Lagging | Elena Marchetti | Semi-annual | No
M-10 | Boundary-affecting changes classified as routine and caught by daily assertion | B | Leading | Trevor Kim | Monthly | No
M-11 | Critical security control failures — CSC-1 to CSC-10 — and time to restore | C | Lagging | Marcus Hale | Monthly | No
M-12 | Daily drift assertions passing — DA-1 to DA-6 and CA-1 to CA-6 | C | Leading | Trevor Kim | Daily | No
M-13 | Automated log-review queue items adjudicated within the day | C | Lagging | Marcus Hale | Daily | No
M-14 | Critical and high patches applied within one month of release | C | Lagging | Trevor Kim | Monthly | No
M-15 | Multi-factor authentication coverage on all access into the CDE | C | Lagging | Trevor Kim | Monthly | No
M-16 | Shared and break-glass account population, reconciled across both registers | C | Leading | Trevor Kim | Quarterly | No
M-17 | Privileged sessions originating from a privileged access workstation | C | Lagging | Trevor Kim | Monthly | No
M-18 | Payment-page tamper alerts raised, and time from change to alert | C | Lagging | Sonia Rendell | Weekly | No
M-19 | Quarters closed with a passing external scan on record | D | Lagging | Owen Castellanos | Quarterly | Yes — BSC-04
M-20 | Authenticated internal scan coverage of in-scope components | D | Lagging | Marcus Hale | Quarterly | No
M-21 | Penetration test findings outstanding beyond their remediation date | D | Lagging | Marcus Hale | Annual | Yes — BSC-05
M-22 | Segmentation test findings reaching an in-scope zone | D | Lagging | Trevor Kim | Annual | No
M-23 | Detection rules validated at the quarterly controlled execution | D | Leading | Marcus Hale | Quarterly | No
M-24 | POI device inspection coverage across 1,914 terminals | D | Leading | Adaeze Nwosu | Quarterly | No
M-25 | Third-party providers with current validation evidence on file under 12.8.4 | E | Lagging | Owen Castellanos | Quarterly | Yes — BSC-07
M-26 | Contractual response-time commitments held for incident-driven provider action | E | Lagging | Frank Mueller | Quarterly | Yes — BSC-09
M-27 | Controls whose operation depends on a contract clause, by clause renewal date | E | Leading | Frank Mueller | Quarterly | Yes — BSC-10
M-28 | Compliance cost against plan — programme envelope and BAU run rate | E | Lagging | Raymond Voss | Quarterly | Yes — BSC-08
M-29 | Security awareness completion against the 95% charter bar | F | Lagging | Owen Castellanos | Annual | No
M-30 | Unannounced repair-personnel identity tests passed | F | Leading | Adaeze Nwosu | Quarterly | No
M-31 | Phishing simulation report rate and click-through | F | Leading | Marcus Hale | Semi-annual | No
M-32 | Incident records by severity, and incidents involving account data | F | Lagging | Marcus Hale | Monthly | No
M-33 | Incident response capability proved against a real compromise of account data | F | Lagging | Naomi Bhatt | Annual | Yes — BSC-12
M-34 | Risk register entries rated High | F | Lagging | Naomi Bhatt | Monthly | Yes — BSC-03

## Board Scorecard
The Board Scorecard at Programme Close — 8 Green · 3 Amber · 1 Red
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
Position | Measure | RAG | Note
Green | Eight measures | GREEN | Validation status, exceptions, evidence, testing, awareness, provider assurance, register position and cost — all at or ahead of target
Amber 1 | Contractual response-time commitment from the token provider | AMBER | OI-07-01. Marketa asked; TRUVANCE DECLINED at renewal. The operational runbook is the only instrument. Carried as BAU-01
Amber 2 | The residual at R-36 is contractual, not technical | AMBER | The right to scan nine appliances is a clause with a renewal date. BAU-02 — replacement of the appliance class — is the treatment
Amber 3 | Three compensating controls, none with a vendor remediation roadmap | AMBER | Each must be re-argued annually. The moment Verition ships a release lifting the 10-character cap, CCW-01 stops being a compensating control and becomes an unremediated finding
**Red** | **Incident response capability proved against a real compromise of account data** | **RED** | Red because IT HAS NEVER HAPPENED. 512 incident records, 5 SEV-2, 0 SEV-1, no breach. R-43 has not moved in any phase of this programme. ADR-0035 keeps it on the scorecard

## What A Metric Cannot Tell You
Four Numbers That Were Green, and What They Did Not Predict
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
The number | Value | What it did not predict | What found it instead
Security awareness completion | 97.1% | Two call-centre agents who would have deleted a recording containing account data rather than reporting it | A tabletop exercise designed by somebody who did not write the plan
POI device inspection coverage | 99.56% | Two of nine unannounced repair-personnel identity tests failing | The identity tests themselves — a second instrument, run unannounced
Automated log review health | Dashboard green | A detection rule reporting itself healthy for 57 hours while its source was stopped | Secondary assertion under CSC-9, and the quarterly controlled execution
Payment-page script inventory | 38 of 38 authorised | A vendor releasing a new version of an authorised script before the contractual notification arrived | 11.6.1 — a detective control evaluating what the consumer browser actually received