## Assessor Observations
The Seventeen Assessor Observations — Every One Adopted or Declined in Writing
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
ID | Observation | Requirement | Owner | Disposition | Closed
OBS-01 | The 12.5.1 monthly reconciliation compares presence of an entry but not the content of the function-and-use field — the condition behind IFC-2 | 12.5.1 | Owen Castellanos | Adopted | 2027-03-31
OBS-02 | The six un-baselined SaaS control planes are governed by contract and configuration review rather than by a configuration standard | 2.2 | Trevor Kim | Adopted with amendment | 2027-05-15
OBS-03 | Two payment page scripts remain served from a third-party origin rather than the Marketa tag proxy — tracked as OI-06-03 | 6.4.3 | Sonia Rendell | Adopted | 2027-03-24
OBS-04 | The exercised-privilege report identifying unexercised entitlements has run once and has one data point | 7.2.5 | Elena Marchetti | Declined | 2027-02-27
OBS-05 | The shared-account population is 20, not 11. The nine appliance built-in administrative accounts were governed under the appliance inventory and the eleven enterprise break-glass identities under the identity store, with no reconciliation between the two registers | 8.2.2 | Trevor Kim | Adopted | 2027-04-17
OBS-06 | Detection rule coverage against adversary technique classes has thirteen surfaces recorded as untested rather than tested and clear | 10.4 | Marcus Hale | Adopted | 2027-03-31
OBS-07 | The daily review queue rota has no automated ownership assignment — the condition behind IFC-7 | 10.4.1.1 | Marcus Hale | Adopted | 2027-04-30
OBS-08 | The four documented scan policy exclusions are reviewed quarterly; three have been unchanged since programme start and carry no expiry | 11.3.1 | Marcus Hale | Adopted | 2027-03-13
OBS-09 | Segmentation testing is annual with a change trigger; the store estate's rate of change makes the trigger, not the calendar, the load-bearing control | 11.4.5 | Trevor Kim | Declined | 2027-01-22
OBS-10 | The payment page tamper-detection proof-of-life test has been performed twice, and the second was slower than the first — tracked as OI-06-04 | 11.6.1 | Sonia Rendell | Adopted | 2027-03-06
OBS-11 | Provider monitoring is quarterly against an annual floor; the largest provider carries no right of inspection | 12.8.4 | Owen Castellanos | Adopted with amendment | 2027-06-24
OBS-12 | The incident response plan has never been activated for a confirmed compromise of account data | 12.10 | Naomi Bhatt | Adopted | 2027-06-24
OBS-13 | The acquirer-notification path depends on a third party's enumeration with no contractual response-time commitment — tracked as OI-07-01 | 12.10.5 | Frank Mueller | Adopted | Not closed — BAU-01
OBS-14 | Awareness completion is measured on a denominator including personnel who are not yet late; the practice is correct and is not documented as a standard | 12.6.3 | Owen Castellanos | Adopted with amendment | 2027-04-30
OBS-15 | At two sampled stores, the inspection log is stored in the back office rather than in the central record until the cycle closes | 9.5.1 | Adaeze Nwosu | Declined | 2027-02-13
OBS-16 | At one sampled store, the back-office equipment cabinet key is held on a general store keyring rather than under separate control | 9.1 | Adaeze Nwosu | Adopted | 2027-01-30
OBS-17 | Store personnel could describe the account-data reporting instruction but not where the procedure document itself is published | 12.10.7 | Adaeze Nwosu | Adopted | 2027-02-27

## Open Items at Close
The Eleven Open Items — 8 On Time · 2 Late · 1 Not Closed
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
ID | Item | Owner | Due | Outcome | Closed
OI-06-03 | SCR-29 and SCR-33 migrated onto the Marketa tag proxy | Sonia Rendell | 2027-03-31 | Closed on time — 7 days early | 2027-03-24
OI-06-04 | The 11.6.1 matrix change verified by a further proof-of-life test | Sonia Rendell | 2027-01-31 | Closed — 34 days late. Already 18 days overdue at the Phase 08 handover, and reported as overdue rather than re-dated | 2027-03-06
OI-06-05 | CAP-05 — the legacy pre-shared key population to zero | Trevor Kim | 2027-06-30 | Closed on time — 18 days early. 214 → 0, the static WPA2-PSK decommissioned and the SSID withdrawn | 2027-06-12
OI-06-06 | TPSP-06's first full 12.8.4 annual review | Owen Castellanos | 2027-06-30 | Closed on time — 6 days early | 2027-06-24
OI-06-07 | A phishing and pretext-calling test programme for 2027 | Marcus Hale | 2027-06-30 | Closed on time — 12 days early. Two full campaigns and 3 pretext-calling tests | 2027-06-18
OI-06-08 | Contract remedy for the SCR-29 change-notification failure at renewal | Frank Mueller with Sonia Rendell | 2027-02-28 | Closed — 40 days late. The renewal date was the vendor's, not Marketa's, and the item was written against a date Marketa did not control | 2027-04-09
OI-06-09 | The four undetected techniques' new rules validated at the next quarterly controlled execution | Marcus Hale | 2027-03-31 | Closed on date, with a residual: 3 of 4 rules validated. The fourth carries to BAU-03 | 2027-03-31
OI-06-10 | The second annual segmentation penetration test — R-14's continuing assurance | Trevor Kim | 2027-05-31 | Closed on time — 10 days early. 6 findings, 0 Critical, 0 reached from Z3 | 2027-05-21
OI-07-01 | A contractual response-time commitment from Truvance for incident-driven token resolution | Frank Mueller with Owen Castellanos | 2027-03-31 | NOT CLOSED. Truvance declined at renewal. The operational runbook remains the only instrument. Carried to BAU-01 | —
OI-07-03 | The 100 directory records with no person behind them | Trevor Kim | 2027-02-28 | Closed on time — 2 days early. All 100 reconciled; none held an entitlement | 2027-02-26
OI-07-04 | The first full seasonal peak under DLP enforcement and the store payment-link route | Adaeze Nwosu with Marcus Hale | 2027-02-28 | Closed on time — 1 day early. 4 customer-initiated instances, all quarantined at the collector, none reaching a store colleague | 2027-02-27

## Carried to BAU
Three Items That Do Not Close With the Programme
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 09 · Illustrative Portfolio Sample
ID | Item | Origin | Owner | Why it does not close | Next date
BAU-01 | A contractual response-time commitment from Truvance for incident-driven token resolution | OI-07-01 | Frank Mueller with Owen Castellanos | MARKETA ASKED AND THE PROVIDER DECLINED. The programme cannot close it, does not close it, and does not re-word it into something closable. The operational runbook remains the only instrument | 2028-03-31 renewal
BAU-02 | Route B — replacement of the vendor-locked appliance class | 08.12 · R-36 | Trevor Kim | 11.3.1.2 is met because a contract clause says Marketa may obtain credentials. A control that depends on a clause has a renewal date, and Route B is what makes the clause unnecessary | FY2028 store refresh
BAU-03 | The fourth undetected technique's detection rule, validated at a controlled execution | OI-06-09 | Marcus Hale | Three of four rules were validated at the March 2027 controlled execution. The fourth was not, and the item is carried with its residual rather than closed on three quarters of the work | 2027-09-30