## ASV Scans
11.3.2 external ASV scanning — four quarterly scans, and the one that failed
Sable Ridge Scanning Services — the same firm as the QSA, under the documented independence position in ADR-0003
Quarter | Scan date | Result | Findings | Rescan | Attestation issued
Q1 | 2026-02-17 | FAIL | 3 — one insecure TLS configuration (automatic-failure condition), one outdated web server version at CVSS 7.5, one missing reverse-proxy patch at CVSS 5.3 | Clean rescan 2026-02-28 — 11 days from the failing scan | 2026-03-06
Q2 | 2026-05-19 | PASS | 0 failing · 14 informational below the 4.0 threshold | Not required | 2026-05-28
Q3 | 2026-08-18 | PASS | 0 failing · 9 informational below the 4.0 threshold | Not required | 2026-08-27
Q4 | 2026-11-17 | PASS | 0 failing · 11 informational below the 4.0 threshold | Not required | 2026-11-26

## Why Q1 Matters
The failed quarter is the most useful evidence in the phase
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 06 · Illustrative Portfolio Sample
Item | Position | Reasoning
The Q1 failure is the point | Three findings; rescanned clean in **11 days** | It was reported to Cardinal Merchant Bank as a failure. It was not quietly rescanned and reported as a pass
Why that matters structurally | Sable Ridge is both QSA and ASV (ADR-0003) | The obvious objection to a same-firm arrangement is that scan findings get softened to help the ROC. **A reported failure is the evidence the arrangement works** — the ASV attestation is issued to the acquirer independently of Marketa
Root cause | A marketing subdomain repointed to a stale-image edge host | No scope-delta review ran on the DNS change. Mapped to R-33 and fed the significant-change definition in 04.08
What a passing scan requires | No vulnerability scoring at or above the ASV threshold, plus no automatic-failure condition regardless of score | A 'clean' scan is a defined technical outcome, not an assessor's opinion
11.3.2.1 change-driven scans | 15 performed during the year | These **may** be performed by qualified internal or external personnel — an ASV is not required for the change-driven scan, only for the quarterly