## Risk Movement
What Phase 06 moved — and why R-01 could not move until now
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 06 · Illustrative Portfolio Sample
Risk | Baseline | Movement | Residual | The evidence it moved on
R-01 — unauthorised or malicious script on a payment page | High 20 — L4 × I5 | Likelihood 4 → 2. Impact held at 5 | Moderate 10 | The completion of the script control. Likelihood 4 was measured, not estimated — three unauthorised scripts were executing at first inventory. The container is removed, the capability no longer exists in the console, the CSP denies its origin, and a recurrence is now detected from outside in minutes: 214 alerts in 140 days, median 9 minutes, 0 exceeding the 24-hour ceiling, 3 incidents, 21 control conditions, and two proof-of-life tests. Impact does not fall while Marketa serves a page into a browser it does not control on a channel carrying 15.7M transactions a year
R-09 — third-party service provider concentration | High 15 — L3 × I5 | Likelihood 3 → 2. Impact held at 5 | Moderate 10 | A full year of six-provider assurance: 36 MT-1 verifications, four signed matrices resolving disagreements before signature, four passed handover tests, per-collection certificate reconciliation, and the AOC scope-statement change detected at review before the provider raised it. No Marketa control reduces the consequence of a Truvance compromise, and 06.10 §8 says so
R-10 — a provider's validation lapses inside the compliance year | Moderate 12 — L3 × I4 | Likelihood 3 → 2. Impact 4 → 3 | Low 6 | Monthly verification against authoritative published sources for the three providers whose validation holds up a scope reduction; a 60-day pre-expiry watch; and the suspension rule recorded in advance, which is what reduces impact: a lapse is now a defined change in the assessed position rather than an improvised argument under deadline pressure
R-19 — decommissioned assets remain powered, reachable and unscanned | Moderate 9 — L3 × I3 | Likelihood 3 → 2 | Low 6 | Twelve monthly reconciliations of the scanner target list against the 02.09 register with 71 of 71 scanned every quarter; CSC-10 making a reconciliation failure a 10.7.2 event; a register entry producing no scan in the period treated as a finding
R-26 — cloud logging disabled, diverted, or not monitored for absence | Moderate 8 — L2 × I4 | Likelihood 2 → 1 | Low 4 | The trail logs its own modification; the object-locked archive copy exists within seconds and cannot be reached by a later disabling act; the silence alert is independent of agent health; F-14 is the recorded instance of the class, found by CSC-7 detection rather than by absence
R-34 — the payment-page script inventory drifts as tooling is added | Moderate 12 — L4 × I3 | Likelihood 4 → 2 | Low 6 | The mechanism is removed rather than governed; payment-template publication no longer exists as a console capability; four reconciliation mechanisms; and TAM-2 detecting an unrecognised script from the consumer's position in 14 minutes — which it did once, finding a Marketa release-process failure

## The Script Control Completes
6.4.3 plus 11.6.1 — the payoff the portfolio has been setting up since Phase 02
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 06 · Illustrative Portfolio Sample
Control | Delivered | What it does | What it cannot do
6.4.3 — preventive | Phase 04 | Authorise each script, bind its integrity at deployment, inventory it with written justification | **Cannot** detect that an authorised third-party script was modified at its origin afterwards
11.6.1 — detective | Phase 06 (this phase) | Continuously evaluate payment pages as received by the consumer browser — headers, DOM and script content — against an approved baseline, alerting inside 24 hours | **Cannot** prevent the modification. It tells you it happened
**Together** | **The control is complete** | Preventive plus detective. Neither alone was sufficient, and the portfolio said so in Phase 04 rather than claiming completion early | **R-01 moves High 20 → Moderate 10** — likelihood 4 → 2, impact held at 5

## Still High
The two risks that do not move, and the two Not in Place findings behind them
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 06 · Illustrative Portfolio Sample
Risk | Standing | Why | Note
**R-36** — components that cannot accept credentialed scanning | **High 16 — HELD** | **11.3.1.2 is Not in Place** on 9 of 71 components. Remediation dated 2027-01-31; becomes CAP-06 | A compensating control was **not** argued — the same discipline the portfolio applied to 8.6.2 in Phase 05
**R-17** — embedded credentials | **High 16 — HELD** | The **8.6.2 Not in Place** finding from Phase 05. Two legacy batch integrations, dated 2027-01-31 | Both Not in Place findings share a remediation date and a re-assessment window with no float