## Phase 07 Movement
The five risks Phase 07 moved — each on an exit criterion published in advance
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 07 · Illustrative Portfolio Sample
Risk | Entering Phase 07 | Movement | Residual | The evidence it moved on
R-14 | High 16 — L4 × I4 — segmentation controls in the store estate are not effective | L 4 → 2; I 4 → 3 | Low 6 | Its own published exit criterion, met. 03.11 §4 set it in Phase 03, before the first test was run: *a clean re-test plus 90 consecutive days with no segmentation-determining divergence across 482 stores.* The May test failed, remediation followed, the June re-test passed, the count was reset on 2026-07-03 by a real recurrence at store 0629, restarted, and ran clean to completion on 2026-10-01. The September confirmatory limb passed at 11 tester-selected stores. CSC-8 asserts the state daily and has itself failed once — F-18, four days — and that failure was caught and answered retrospectively against retained snapshots. Impact 4 → 3 because the path the test proved was Z7 to Z5, guest wireless into a connected-to store zone, while the Z3-to-Z1 crossing into the CDE is separately enforced at an inline prevention point with fifteen months of flow recording
R-31 | High 16 — L4 × I4 — historical account data persists in the call-recording estate and other unstructured stores | L 4 → 2; I 4 → 3 | Low 6 | Its own published exit criterion, met. 03.11 §4 required *a second full discovery run across the same populations returning nothing*, due 2026-08-31. Performed 2026-08-17 to 2026-08-28 across the same 1,842 systems, 41 shares, 6 archives and the restored backup sets, returning zero account data instances. Halberd certificates of destruction on file for the disposed populations; the 33 immutable backup sets aged out 2026-05-31, verified by catalogue evidence. Impact 4 → 3 because the historical corpus is destroyed and evidenced; the residual is the forward-only creation path, held down by DTMF suppression, DLP telemetry, quarterly unowned-repository discovery and the collector-side quarantine rule — the detective layer 07.11 §7 exists to keep an empty set empty
R-02 | High 15 — L3 × I5 — POI device tampering, skimmer overlay or whole-device substitution | L 3 → 2; impact held at 5 | Moderate 10 | Four full quarterly inspection cycles at all 1,914 terminals with no sampling — 7,656 device-inspections. The mechanism produced findings rather than silence: six seal discrepancies in Q3, all at distinct stores, all cleared as maintenance, and the procedure tightened anyway under ADR-0018. 9.5.1.3 training at 98.1%, unabridged for the seasonal cohort under SEA-5 and ADR-0019. Colleague-raised POI reports rose from 4 to 27, which is the outcome signal 07.04 §7.3 treats as the programme's best. IR-P3 gives the finder a route that does not require judgement. Impact held at 5: a substituted device captures data before the SRED function ever sees it
R-05 | High 15 — L3 × I5 — a P2PE condition fails at one or more stores | L 3 → 2; impact held at 5 | Moderate 10 | The 2026 annual scope confirmation re-verified all nine P2PE conditions and all nine held — 07.06 §7. Verition's Council listing verified twice under MT-1; PIM adherence obligations made contractual; the daily per-store POI-to-VLAN assertion under CSC-8; the three non-conforming stores of February 2026 closed with no recurrence across four inspection cycles. Impact held at 5: a P2PE failure invalidates the reduction that removes 1,914 lanes and 482 store servers from the assessed population, and no control Marketa operates changes that consequence
R-27 | High 15 — L3 × I5 — administrative-services zone concentration | L 3 → 2; impact held at 5 | Moderate 10 | The thinnest movement in the phase, and §4 says so. The population holding Z3 administrative authority fell as two legacy administrative jump hosts were retired on completion of the privileged access broker rollout, recorded as removals in the 12.5.2 reconciliation. SCN-3 enhanced screening was extended to the 178 in-scope administrative personnel although 12.7.1's wording does not compel it. Phishing-resistant FIDO2 covers every administrative path. The 12.3.4 technology review found no unsupported component on the Z3 path and the 12.3.3 review removed TLS 1.0 and 1.1 across it. Impact held at 5: the concentration is a deliberate design trade under principle SP-4 and is unchanged

## Trajectory
The register across the whole programme — entering the assessment at 2 High
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 07 · Illustrative Portfolio Sample
Point | High | Moderate | Low | Total | What moved it
Phase 03 — baseline | 9 | 21 | 14 | 44 | The register as identified and scored
Phase 04 — Requirements 2–6 | 9 | 21 | 14 | 44 | Almost everything held. Three months is not an operating history
Phase 05 — Requirements 7–9 | 8 | 21 | 15 | 44 | R-02 and R-13 reduce; R-17 held by the 8.6.2 finding
Phase 06 — Requirements 10–11 | 7 | 19 | 18 | 44 | R-01 moves at last; R-36 held by the 11.3.1.2 finding
**Phase 07 — Requirement 12** | **2** | **22** | **20** | **44** | **R-14 and R-31 to Low on their published exit criteria; R-02, R-05, R-27 to Moderate**
Expected at close (Phase 09) | 0 | 13 | 31 | 44 | Requires both Not in Place findings to close by 2027-01-31

## The Two Highs
The programme enters its assessment with two Highs and two Not in Place findings — and knows it
Both dated 2027-01-31, against a re-assessment on 2027-02-18. There is no float, and that is stated rather than disguised.
Risk | Description | Rating | Why it is still High | Remediation date
**R-17** | Application and system accounts with embedded credentials | **High 16** | **8.6.2 Not in Place** — two legacy batch integrations, `batch-icq` on CDE-05 and `gl-extract` on CDE-04. A compensating control was argued and **refused** | **2027-01-31**
**R-36** | Components that cannot accept credentialed assessment | **High 16** | **11.3.1.2 Not in Place** — authenticated scanning incomplete on 9 of 71. The QSA rejected the argument that a contractual inability equals a technical one. **No compensating control was argued** | **2027-01-31**