## The 14 TRAs
All fourteen targeted risk analyses, consolidated — 12.3.1, 12.3.2 and the electives
A 12.3.1 analysis sets an entity-defined frequency a requirement permits. A 12.3.2 analysis underpins a customized approach. An elective analysis is one Marketa wrote when the standard did not compel it.
ID | Requirement | Parameter set | Determination | Type | Owner | Delivered in | Next review
TRA-01 | 5.2.3.1 | Frequency of periodic evaluations of system components identified as not at risk from malicious software | Six-monthly, with event triggers on platform change. The 01.11 §6 calendar assumed annual at programme start; the analysis concluded six-monthly and the calendar was amended | 12.3.1 | Marcus Hale | Phase 04 | 2027-04-14
TRA-02 | 5.3.2.1 | Frequency of periodic malware scans where continuous behavioural analysis is not in use | Weekly full scan on the relevant population, with on-access scanning continuous beneath it | 12.3.1 | Marcus Hale | Phase 04 | 2027-04-14
TRA-03 | 7.2.5.1 | Frequency of review of application and system account access and privileges | Every six months, aligned to the 7.2.4 user access review so the two share one evidence cycle | 12.3.1 | Elena Marchetti | Phase 05 | 2027-05-19
TRA-04 | 8.6.3 | Frequency and complexity of password changes for application and system accounts | Determined per account class — four classes, from continuous rotation on vault-retrieved credentials to a bounded interval on the residual legacy population | 12.3.1 | Trevor Kim | Phase 05 | 2027-05-19
TRA-05 | 9.5.1.2.1 | Frequency and type of POI device inspections | Quarterly, full visual and serial verification at all 1,914 terminals — no sampling, because a sampled inspection cycle leaves the unsampled devices uninspected | 12.3.1 | Adaeze Nwosu | Phase 05 | 2027-05-19
TRA-06 | 10.4.2.1 | Frequency of periodic log review for system components not covered by the daily 10.4.1 population | Monthly, risk-weighted by component class — 11 of 71 components, with the other 60 reviewed daily | 12.3.1 | Marcus Hale | Phase 06 | 2027-06-16
TRA-07 | 11.3.1.1 | Time frame for addressing all other applicable vulnerabilities not ranked high or critical | Bounded remediation windows by rank, reviewed monthly, with an automatic escalation on two consecutive scans — the rule fired 43 times and closed every one | 12.3.1 | Marcus Hale | Phase 06 | 2027-06-16
TRA-08 | 11.6.1 | Frequency of the payment-page change- and tamper-detection evaluation | Continuous evaluation with alerting inside 24 hours, against a requirement floor of weekly — 336 times stricter, justified on transaction volume per unit time | 12.3.1 | Sonia Rendell | Phase 06 | 2027-02-10
TRA-09 | 12.10.4.1 | Frequency of training for personnel with incident response responsibilities | Semi-annual for the core response team; annual for the extended roster, with an event trigger on any Critical finding or confirmed incident | 12.3.1 | Marcus Hale | Phase 07 | 2027-07-14
TRA-10 | 12.3.2 — the customized approach for 8.3.9 | Password change frequency replaced by continuous behavioural authentication analytics | Applies to the residual in-scope population where a password remains the sole factor. 8.4.2 MFA removes password-only user access to the CDE, so the scope is connected-to and vendor-managed systems only | 12.3.2 | Trevor Kim | Phase 05 | 2027-03-17
TRA-11 | *Elective* — 6.3.3 | Time frame for applying security patches that are neither critical nor high | Risk-ranked windows by component class — 90 days and 180 days — reconciled with TRA-07 so the two entity-defined timeframes cannot disagree | Elective | Trevor Kim | Phase 06 | 2027-04-14
TRA-12 | *Elective* — 11.4.5 | Whether annual segmentation testing is sufficient given the rate of change across 482 store networks | Annual retained, plus mandatory testing after any segmentation-affecting change. A six-monthly cadence was examined and rejected — 11.4.6 is a service-provider requirement and adopting it would create an obligation Marketa does not have | Elective | Trevor Kim | Phase 06 | 2027-06-16
TRA-13 | *Elective* — 12.8.4 | Whether the annual floor for monitoring provider compliance status is sufficient | Annual formal review plus a quarterly status check and monthly verification (MT-1) for the three providers whose validation holds up a scope reduction | Elective | Owen Castellanos | Phase 06 | 2027-06-16
TRA-14 | *Elective* — 12.5.2 | What constitutes a significant change triggering scope reconfirmation | A defined trigger list — SIG-1 to SIG-10 — applied through change control, with four exclusions named so the definition stays credible. 27 significant changes in the period | Elective | Naomi Bhatt | Phase 07 | 2027-07-14

## The Burden
What fourteen analyses actually cost, stated rather than glossed
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 07 · Illustrative Portfolio Sample
Item | Position | Note
Fourteen analyses | Each reviewed at least every 12 months | This is a real annual maintenance burden, not a one-off document set
Ten compelled | 12.3.1 requirements that permit an entity-defined frequency, plus the single 12.3.2 for the 8.3.9 customized approach | These are not optional. A missing one is a finding
Four elective | 6.3.3 patch windows · 11.4.5 segmentation test frequency · 12.8.4 TPSP monitoring · 12.5.2 what counts as a significant change | Written because a frequency nobody can justify is a frequency nobody will defend — not because the standard demanded it
12.3.3 — cryptographic review | Cipher suites and protocols reviewed at least every 12 months | Separate from the fourteen; a standing annual obligation
12.3.4 — technology review | Hardware and software reviewed at least every 12 months for continued vendor support | Separate from the fourteen; feeds the end-of-life planning