## Control-to-Risk
Control-to-risk traceability — no High risk is untreated
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Risk | Baseline | Treating control(s) | PCI requirement(s) | Delivered by phase | Residual at close
R-06 | Moderate 12 | Quarterly discovery across all repositories including the unowned-repository sweep under procedure P-2; named individual owner and explicit retention rule for every unstructured store; DLP telemetry; data-disposition step in the definition of done for every migration | 3.2.1, 3.3.1, 9.4.1, 12.5.2, 12.10.7 | 02 · 04 · 07 | Moderate
R-07 | Low 6 | Continuous DLP — inbound quarantine and outbound block; quarterly archive search under assumption A-05b; phishing and data-handling awareness; 12.10.7 procedure P-3 | 3.2.1, 12.10.7, 12.6.3, 5.4.1 | 02 · 04 · 07 | Low
R-08 | Moderate 12 | Process-level data mapping extended beyond systems to outputs; dispute handling redesigned into CDE-03 and CDE-06 where images render in session and cannot be saved; quarterly discovery; procedure P-2 | 12.5.2, 3.2.1, 3.3.1, 12.10.7 | 02 · 05 · 07 | Low
R-22 | Moderate 9 | Truvance-hosted payment link for store special orders — the compliant path made faster than the workaround; free-text field filtering; inbound DLP; targeted awareness for store and contact-centre colleagues | 3.2.1, 12.10.7, 12.6.3, 6.4.1 | 02 · 04 · 06 | Low
R-24 | Low 4 | Thirteen-month retention enforced at CT-60 as a platform control rather than a policy; retention rule set under a 12.3.1 targeted risk analysis; annual audio discovery under condition MOTO-C7; legal-hold exception register | 3.2.1, 9.4.7, 12.3.1, 3.1.1 | 02 · 06 | Low
R-31 ‡ | High 16 | Deletion manifest for ~11,400 recordings; retention reduced from seven years to thirteen months; procedure P-1 — any change to a capture-affecting control triggers a retrospective review of what was captured before; DLP live 2026-04-10; a second full discovery run as the exit criterion | 3.2.1, 12.10.7, 9.4.7, 12.3.1, 12.5.2 | 02 · 06 · 07 | Low
R-03 | Moderate 12 | Three-zone store split Z5 / Z6 / Z7; VLAN access control lists at every SVI; `ROLE-POI` port template with port security and a MAC limit of one; NSC-13; assertions DA-2, DA-3, DA-5; 11.4.5 testing with the store estate as a primary target | 1.2.1, 1.3.1, 1.3.3, 1.4.1, 11.4.5 | 03 | Moderate — structural
R-04 | Moderate 12 | Daily drift assertions DA-1 to DA-5 reading the device rather than the controller; four-hour incident response; build-time trunk assertion in SB-4.2; contractor imaging procedure under OI-03-03; negative boundary gate at every rollout wave | 1.2.8, 1.2.2, 2.2.1, 11.4.5 | 03 · 05 | Low
R-14 ‡ | High 16 | Everything in R-03 and R-04, plus: corrected build image SB-4.2; Track A allowed-VLAN restoration at 37 stores; four amended 1.2.2 change classifications; the Boundary Change Authority; the 11.4.5 re-test passed 2026-06-26; and the ninety-day drift exit criterion | 11.4.5, 1.2.2, 1.2.8, 1.3.3, 12.5.2 | 03 · 06 | Low
R-15 | Moderate 12 | Dedicated internet-only VLAN 40 with explicit deny to VLANs 10, 20, 30 and 99; key rotation; population inventoried at 214 devices across 138 stores; 1.2.6 security features register; corrective action CAP-05 eliminating the population in the FY2027 refresh | 2.3.2, 1.3.3, 1.2.6, 11.2.1 | 03 · 06 · 09 | Moderate — until CAP-05 closes
R-27 | High 15 | Two independent enforcement layers on two management planes at every T1 boundary; sixteen named flows and no others; MFA under 8.4.2 on every administrative path; privileged access brokering through CT-11 with session recording; the administrative-path test in the 11.4.5 methodology; 10.2.1 logging of every privileged action | 7.2.2, 8.4.2, 1.3.1, 10.2.1, 11.4.5, 6.3.3 | 03 · 05 · 06 | Moderate — structural
R-12 | Moderate 12 | Dispute images rendered in session and non-savable in CDE-03 and CDE-06; least-privilege role design with the 63-member inherited group dissolved; 7.2.4 six-monthly access review; full 10.2.1 activity logging with automated review under 10.4.1.1; separation of dispute initiation from dispute approval | 7.2.1, 7.2.2, 7.2.4, 8.2.1, 10.2.1, 3.4.1 | 05 · 06 | Moderate
R-13 | Moderate 12 | Time-bounded seasonal accounts with an automatic expiry rather than a leaver process; role templates provisioned by store position; 8.2.6 removal within the defined window; 7.2.4 review scheduled immediately after the season; 12.6.3 training as an access precondition | 8.2.4, 8.2.5, 8.2.6, 7.2.4, 7.2.5, 12.6.3 | 05 · 06 | Moderate — structural
R-17 | High 16 | Inventory of all application and system accounts under 8.6.1; credentials moved to the secrets vault with programmatic retrieval; interactive use prevented; rotation under 8.6.3; the two legacy batch integrations rewritten — the 8.6.2 Not in Place item, remediation dated 2027-01-31 | 8.6.1, 8.6.2, 8.6.3, 2.2.2, 8.3.6 | 04 · 05 · 08 | Low
R-18 | Moderate 12 | NSC-01 management plane on a dedicated out-of-band VLAN; administration of NSCs only from a privileged access workstation brokered through CT-11; 1.5.1 endpoint controls; no clipboard, drive mapping or file transfer through a jump host under 3.4.2; condition SEG-C5 | 1.5.1, 8.4.2, 8.4.3, 7.2.2, 2.2.7 | 03 · 05 | Low
R-21 | Moderate 12 | Automated anti-phishing mechanisms under 5.4.1; MFA on all CDE access under 8.4.2; EDR with tamper protection; no device connects to both an untrusted network and the CDE; 12.6.3 awareness with simulated phishing | 5.4.1, 8.4.2, 12.6.3, 1.5.1, 5.2.1 | 04 · 05 · 07 | Low
R-01 | High 20 | 6.4.3 script inventory, authorisation workflow and integrity assurance across 38 scripts on 6 templates; 11.6.1 change- and tamper-detection alerting within 24 hours; content security policy and subresource integrity; the Truvance iframe keeping the card field off Marketa's origin; incident procedure for a page-integrity event | 6.4.3, 11.6.1, 6.4.1, 6.4.2, 6.5.1, 12.10.1 | 04 · 06 · 07 | Moderate
R-05 | High 15 | P2PE-validated solution with the PIM control checklist; conditions P2PE-C1 to P2PE-C9 with named owners and cadences; VLAN 30 with `ROLE-POI`, port security and a VLAN ACL; quarterly and on-change verification of the POI network path; the affected store recorded as in scope until corrected, as three stores were in February 2026 | 12.5.2, 9.5.1.1, 1.3.1, 11.4.5, 12.8.4 | 02 · 03 · 06 | Moderate — structural
R-23 | Moderate 10 | Fixed media path at the session border controller CT-58; suppression point upstream of Marketa at Cadence; condition MOTO-C2 with change control over any telephony routing change; annual audio discovery; 12.8.5 responsibility matrix with Cadence | 12.5.2, 1.2.2, 3.2.1, 12.8.5, 12.10.7 | 02 · 06 | Low
R-34 | Moderate 12 | Tag manager removed from all six payment templates, confirmed by field telemetry rather than by console setting; script authorisation workflow with a named approver; 11.6.1 monitoring detecting an unauthorised script within 24 hours; change control extended to marketing tooling | 6.4.3, 11.6.1, 6.5.1, 12.6.3 | 04 · 06 | Low
R-35 | Low 6 | Secure development practice under 6.2.1 to 6.2.4; pre-release review and testing; external and internal vulnerability scanning; the storefront holding tokens and order data only, never PAN; the application penetration test of September 2026 | 6.2.1, 6.2.4, 6.3.2, 6.4.1, 11.3.2 | 04 · 06 | Low
R-09 | High 15 | TPSP register with a 12.8.5 responsibility matrix for every provider; 12.8.4 monitoring of validation status; quarterly TPSP review; written acknowledgement under 12.8.2; contractual exit and portability terms; continuity planning that treats a provider outage as a payment-channel outage | 12.8.1, 12.8.2, 12.8.3, 12.8.4, 12.8.5, 12.10.1 | 01 · 06 · 07 | Moderate — structural
R-10 | Moderate 12 | Validation expiry tracked per provider per service consumed, not per provider; Council listing reconciliation; the Verition P2PE Attestation of Validation dated 2025-09-12 tracked as OI-02-03; quarterly review with a named owner; escalation where an expiry falls inside the compliance year | 12.8.4, 12.8.5, 12.5.2 | 01 · 06 | Low
R-11 | Low 6 | Northbridge responsibility matrix enumerating which party detects, triages, escalates and responds, by hour of day; joint escalation testing; 10.4.1 review evidence produced by Marketa regardless of who performed it; contract terms on notification timing | 12.8.2, 12.8.5, 12.10.1, 10.4.1 | 01 · 06 · 07 | Low
R-19 | Moderate 9 | Assessed register reconciled against four independent sources monthly rather than one source annually; decommissioning procedure with a verified power-off, storage disposition and CMDB update; the AWS stopped-instance and retained-volume sweep; 9.4.6 media disposal evidence | 12.5.1, 12.5.2, 9.4.6, 2.2.1, 11.3.1 | 02 · 04 · 06 | Low
R-20 | Moderate 12 | Anti-malware on all applicable systems with 5.3.3 removable-media scanning; EDR with tamper protection; segmented store estate limiting lateral reach; POS store-and-forward preserving trading; backup with restore testing; incident response under 12.10.1 to 12.10.5 | 5.2.1, 5.3.1, 5.3.2, 5.3.3, 12.10.1, 12.10.3, 12.10.5 | 04 · 07 | Moderate — structural
R-29 | Low 6 | Quarterly ASV scanning by Sable Ridge Scanning Services with independence documented; internal pre-scan before each quarterly submission; remediation and rescan tracked against obligation C4's thirty-day window; Q1 2026 failed with 3 findings and rescanned clean in 11 days | 11.3.2, 11.3.2.1, 6.3.3, 6.5.1 | 06 | Low
R-30 | Moderate 12 | Risk-ranked vulnerability management under 6.3.1; one-month patch window under 6.3.3; 11.3.1.1 management of all other applicable vulnerabilities; store patching scheduled to complete before the 2026-09-30 freeze cut-off; emergency patch path that survives the freeze | 6.3.1, 6.3.3, 11.3.1, 11.3.1.1, 6.3.2 | 04 · 06 | Moderate
R-32 | Moderate 12 | Mandatory classification field; the segmentation-affecting change list with four types added in June 2026; scope-delta review; two named approvers; negative boundary verification by a party other than the implementer; automatic 11.4.5 re-test obligation; Boundary Change Authority weekly | 1.2.2, 6.5.1, 11.4.5, 12.5.2, 1.2.3 | 03 · 04 | Low
R-36 | High 16 | Vendor engagement for credentialed access under OI-02-02; compensating position in NSC-EX-02 — vendor account disabled between windows, sessions brokered and recorded, firmware tracked in the TPSP review; unauthenticated scanning maintained meanwhile; the 11.3.1.2 Not in Place item, remediation dated 2027-01-31 | 11.3.1.2, 6.3.3, 2.2.1, 12.8.5, 11.3.1.1 | 06 · 08 | Low
R-16 | Low 6 | 11.2.1 quarterly attested scan across all 488 facilities; continuous over-the-air monitoring from the store access points; 11.2.2 authorised access point inventory correlated to switch and port at CT-48; 12.10.5 incident response on detection — three unauthorised access points found and removed inside a day during the year | 11.2.1, 11.2.2, 12.10.5, 1.3.3 | 03 · 06 | Low
R-26 | Moderate 8 | Log file validation; delivery to an account no CDE principal can write to; deletion denied by service control policy; 10.7.2 alerting on the absence of a log source rather than on its content; CloudTrail and flow logs configured before the event, not after | 10.2.1, 10.3.2, 10.3.4, 10.5.1, 10.7.2 | 03 · 06 | Low
R-28 | Moderate 12 | 10.4.1.1 automated log review mechanisms; heartbeat reconciliation and log volume banding; rule and parser health monitored as a control in its own right; 10.7.3 response to a detection failure; independent periodic validation that a known test event produces an alert | 10.4.1, 10.4.1.1, 10.4.2, 10.7.2, 10.7.3 | 06 | Low
R-37 | Low 6 | 11.5.2 change-detection on CDE components with baselines re-established as a change completion criterion; agent health monitored under 10.7.2; exclusions reviewed and approved rather than added; critical file comparison at least weekly | 11.5.2, 10.3.4, 10.7.2, 6.5.1 | 04 · 06 | Low
R-25 | Moderate 12 | Boundary defined only in the CT-30 infrastructure-as-code repository; console changes to boundary resources denied by service control policy; DA-6 continuous plan-diff; five principals with boundary-modifying permissions, reduced from fourteen; identity-path reachability analysis; automatic 11.4.5 re-test on a boundary merge | 1.2.2, 1.2.8, 10.2.1, 11.4.5, 7.2.2 | 03 · 06 | Moderate — structural
R-02 | High 15 | 9.5.1 quarterly inspection cycle across 1,914 terminals, designed to be executed by store colleagues on shift rather than by visiting engineers; 9.5.1.1 device register reconciled monthly to Verition telemetry; 9.5.1.2 inspection method and 9.5.1.2.1 frequency set by targeted risk analysis; 9.5.1.3 colleague training; 12.10.4 incident path — 6 seal discrepancies found in Q3, all cleared as maintenance, procedure tightened | 9.5.1, 9.5.1.1, 9.5.1.2, 9.5.1.3, 12.10.4, 12.6.3 | 05 · 06 | Moderate — structural
R-38 | Low 6 | 9.1.1 and 9.2.1 physical access controls at store back-of-house; cabinet locks with key control; 9.3.1 authorisation for personnel access; visitor and contractor handling; port security and `ROLE-UNUSED` shutting every unused port so that physical access alone yields no network position | 9.1.1, 9.2.1, 9.2.2, 9.3.1, 9.5.1 | 03 · 05 | Low
R-39 | Low 6 | Halberd Data Destruction certificates of destruction as 9.4.7 evidence; retention and disposal policy with a named owner per repository; secure containers for hardcopy at stores and the contact centre; 9.4.5 and 9.4.6 disposal procedure with reconciliation | 9.4.5, 9.4.6, 9.4.7, 3.2.1 | 05 · 07 | Low
R-33 | Moderate 12 | 12.5.2 annual scope confirmation with all seven elements; 12.5.1 inventory reconciled monthly against four sources; scope-delta review inside change control; merchant identifier reconciliation with Cardinal; pre-engagement notification for any new TPSP under obligation C9 | 12.5.1, 12.5.2, 6.5.1, 12.8.1 | 02 · 03 · 06 | Low
R-40 | Low 4 | 12.6.3 awareness at hire and at least annually with a ≥95% charter bar; seasonal module delivered as an access precondition; role-specific content for POI inspection and payment handling; 12.6.3.1 threat-specific content on phishing and social engineering — actual completion 97.1% | 12.6.1, 12.6.2, 12.6.3, 12.6.3.1 | 07 | Low
R-41 | Low 6 | Roadmap sequenced backwards from CON-04's fixed fieldwork window; store-side critical path completing by 2026-09-30; weekly PCI Working Group tracking; 11.4 FTE resourcing with named contributions; escalation of any control at risk of missing its operating-history window | 12.1.1, 12.4.1, 12.5.2 | 01 · 09 | Low
R-42 | Low 6 | Evidence standard E1 to E5 applied from Phase 02 onward; every artefact dated, attributed and population-bounded; twelve-month retention of penetration testing results and remediation activities under 11.4.1; evidence store indexed to the 306 applicable sub-requirements | 12.5.2, 11.4.1, 10.5.1, 12.1.1 | 02 · 08 | Low
R-43 | Low 6 | Five 12.10.7 procedures P-0 to P-4 for PAN discovered where it is not expected; incident response plan tested under 12.10.2; scenario exercises covering POI substitution, rogue access point, page-integrity event and failed segmentation boundary; 12.10.4 training for responders | 12.10.1, 12.10.2, 12.10.4, 12.10.5, 12.10.7 | 07 | Low
R-44 | Low 4 | 10.6.1 to 10.6.3 time synchronisation from CT-62 only, with NSC-11 asserting the source on every NSC; log source heartbeat reconciliation; 10.7.2 alerting on absence; 10.5.1 twelve-month retention with three months immediately available | 10.6.1, 10.6.2, 10.6.3, 10.7.2, 10.5.1 | 04 · 06 | Low

## Expected Movement
Expected Register Movement Across the Programme
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Band | Baseline (Phase 03) | Expected at close (Phase 09) | Change | Note
High | 9 | 0 | −9 | Every High risk is treated by a control delivered in Phases 04 to 08
Moderate | 21 | 13 | −8 | Eight move to Low; several structural residuals are held deliberately
Low | 14 | 31 | +17 | The band grows because risks move down into it, not because risks disappear
Total | 44 | 44 | 0 | No risk is removed from the register. Ratings move; entries do not vanish

## Structural Residuals
Risks that will never fully reduce — stated because a register implying otherwise is not credible
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Structural residual | Why it cannot be eliminated | Treatment stance
482-store estate | A change that takes ten minutes per store is 80 hours of field effort. Consistency across 482 sites is a permanent operating problem, not a project | Reduce through central deployability and drift detection; never eliminated
TPSP concentration | Three providers now sit between Marketa and its ability to accept payment at all. Scope reduction created this — it converted a technical control problem into a third-party assurance problem | Managed under Requirement 12.8 and 12.9 in Phase 06; the dependency itself is permanent
Seasonal workforce | Up to 6,800 temporary colleagues join during the freeze, precisely when transaction volume peaks and change is prohibited | Reduce through onboarding controls and awareness; the population turns over every year
Vendor-locked appliances | A subset of store back-office appliances cannot accept credentialed scanning without vendor cooperation | Becomes CAP-06 at the assessment; closes only with vendor agreement or replacement