## Risk Register
The baseline risk register — 44 risks · 9 High · 21 Moderate · 14 Low
Likelihood 1-5 x Impact 1-5. High >= 15 · Moderate 8-12 · Low <= 6. Impact is scored on cardholder data exposure, brand-programme penalties AND business interruption.
ID | Risk | Category | L | I | Score | Rating | Owner | Treating requirement(s)
R-01 | Unauthorised or malicious script executing in the consumer browser on a payment page harvests card data before it reaches the Truvance iframe — PAN never touches a Marketa server and Marketa is still the party that served the page | Payment Channel | 4 | 5 | 20 | High | Sonia Rendell | 6.4.3, 11.6.1, 6.4.1, 6.4.2, 6.5.1, 12.10.1
R-02 | POI device tampering, skimmer overlay or whole-device substitution across 1,914 terminals in 482 buildings that are unattended overnight and staffed by a workforce that turns over seasonally | Physical &amp; Device | 3 | 5 | 15 | High | Adaeze Nwosu | 9.5.1, 9.5.1.1, 9.5.1.2, 9.5.1.3, 12.10.4, 12.6.3
R-03 | Store network flatness — the store fabric is one switch performing inter-VLAN routing, so guest, colleague, operations, payment-device and management traffic are separated by a single configuration layer with no second enforcement plane | Network &amp; Segmentation | 3 | 4 | 12 | Moderate | Trevor Kim | 1.2.1, 1.3.1, 1.3.3, 1.4.1, 11.4.5
R-04 | Configuration drift returns to the store estate faster than assurance detects it, because 482 sites are maintained by field engineering and local contractors carrying their own stock configurations | Network &amp; Segmentation | 3 | 4 | 12 | Moderate | Trevor Kim | 1.2.8, 1.2.2, 2.2.1, 11.4.5
R-05 | A P2PE condition fails at one or more stores — a POI patched into the general data VLAN, an unlisted device, a lapsed solution listing — invalidating the card-present scope reduction that removes 1,914 lanes and 482 servers from the assessed population | Payment Channel | 3 | 5 | 15 | High | Adaeze Nwosu | 12.5.2, 9.5.1.1, 1.3.1, 11.4.5, 12.8.4
R-06 | New unstructured repositories — shares, sites, document stores, ticket attachments — accumulate account data faster than quarterly discovery finds them | Account Data | 3 | 4 | 12 | Moderate | Marcus Hale | 3.2.1, 3.3.1, 9.4.1, 12.5.2, 12.10.7
R-07 | Account data arrives in the messaging and collaboration estate from a customer or a colleague and comes to rest in a mailbox or archive | Account Data | 2 | 3 | 6 | Low | Marcus Hale | 3.2.1, 12.10.7, 12.6.3, 5.4.1
R-08 | Account data is created as a by-product of a business process nobody has mapped — a report, an export, a reconciliation artefact, a scanned attachment | Account Data | 3 | 4 | 12 | Moderate | Elena Marchetti | 12.5.2, 3.2.1, 3.3.1, 12.10.7
R-09 | Third-party service provider concentration — Truvance Payments is hosted checkout, gateway and the single token vault across card-present, e-commerce and MOTO simultaneously; a failure, breach or contractual discontinuity at one provider affects every channel at once | Third Party | 3 | 5 | 15 | High | Owen Castellanos | 12.8.1, 12.8.2, 12.8.3, 12.8.4, 12.8.5, 12.10.1
R-10 | A provider's validation lapses inside the compliance year — a P2PE Attestation of Validation, a service provider AOC, or a Council listing — and Marketa continues to rely on a reduction that no longer has a basis | Third Party | 3 | 4 | 12 | Moderate | Elena Marchetti | 12.8.4, 12.8.5, 12.5.2
R-11 | Responsibility gap between Marketa and Northbridge Managed Services for after-hours detection, triage and escalation, such that an event is seen by neither party | Third Party | 2 | 3 | 6 | Low | Marcus Hale | 12.8.2, 12.8.5, 12.10.1, 10.4.1
R-12 | Insider misuse in dispute, chargeback and refund handling, where full PAN is legitimately visible to a person doing their job and the control is authorisation and monitoring rather than elimination | Identity &amp; Access | 3 | 4 | 12 | Moderate | Elena Marchetti | 7.2.1, 7.2.2, 7.2.4, 8.2.1, 10.2.1, 3.4.1
R-13 | Seasonal workforce access — up to 6,800 temporary colleagues onboarded at speed in October and offboarded slowly or not at all in February, inside the change freeze and at peak transaction volume | Identity &amp; Access | 4 | 3 | 12 | Moderate | Adaeze Nwosu | 8.2.4, 8.2.5, 8.2.6, 7.2.4, 7.2.5, 12.6.3
R-14 | ‡ Segmentation controls in the store estate are not effective, permitting a lower-trust zone to reach a governed zone. Raised on evidence 2026-05-18 under ADR-0005, on the disproof of the assumption that configuration verification across 482 sites establishes segmentation effectiveness | Network &amp; Segmentation | 4 | 4 | 16 | High | Trevor Kim | 11.4.5, 1.2.2, 1.2.8, 1.3.3, 12.5.2
R-15 | The legacy pre-shared key remnant — 214 store appliances at 138 stores sharing one static WPA2-PSK that cannot be revoked for one holder, attributed to one holder, or rotated without a field operation across 138 sites | Network &amp; Segmentation | 3 | 4 | 12 | Moderate | Trevor Kim | 2.3.2, 1.3.3, 1.2.6, 11.2.1, CAP-05
R-16 | An unauthorised wireless access point is installed in a store — by a colleague solving a coverage problem or by an adversary — and is not detected before the next quarterly scan | Monitoring &amp; Detection | 2 | 3 | 6 | Low | Trevor Kim | 11.2.1, 11.2.2, 12.10.5, 1.3.3
R-17 | Application and system accounts hold embedded, non-rotatable credentials in legacy batch integrations, with interactive use possible and no individual attribution | Identity &amp; Access | 4 | 4 | 16 | High | Trevor Kim | 8.6.1, 8.6.2, 8.6.3, 2.2.2, 8.3.6
R-18 | Privileged access to an NSC management plane — including CT-48, which determines the segmentation state of 978 store systems and 1,914 POI devices — is obtained from a workstation that also carries general network and email access | Identity &amp; Access | 3 | 4 | 12 | Moderate | Trevor Kim | 1.5.1, 8.4.2, 8.4.3, 7.2.2, 2.2.7
R-19 | Assets recorded as decommissioned remain powered, network-reachable or holding retained storage, and are therefore excluded from scanning, patching and monitoring while still being part of the estate | Vulnerability &amp; Change | 3 | 3 | 9 | Moderate | Trevor Kim | 12.5.1, 12.5.2, 9.4.6, 2.2.1, 11.3.1
R-20 | Destructive or extortion malware interrupts trading across the store estate or the distribution network, with recovery competing against the trading calendar | Vulnerability &amp; Change | 3 | 4 | 12 | Moderate | Marcus Hale | 5.2.1, 5.3.1, 5.3.2, 5.3.3, 12.10.1, 12.10.3, 12.10.5
R-21 | Phishing delivers a foothold in corporate end-user computing that is used to reach administrative services and, from there, the brokered path toward the CDE | Identity &amp; Access | 4 | 3 | 12 | Moderate | Marcus Hale | 5.4.1, 8.4.2, 12.6.3, 1.5.1, 5.2.1
R-22 | Customer-initiated account data arrives by email, web form free-text field or special-order note, creating PAN in a system that was never designed to hold it | Account Data | 3 | 3 | 9 | Moderate | Bill Traynor | 3.2.1, 12.10.7, 12.6.3, 6.4.1
R-23 | A telephony routing or platform change moves the DTMF suppression point downstream of Marketa, putting spoken account data into Marketa's telephony and recording estate — condition MOTO-C2 | Payment Channel | 2 | 5 | 10 | Moderate | Bill Traynor | 12.5.2, 1.2.2, 3.2.1, 12.8.5, 12.10.7
R-24 | Call recordings are retained beyond the thirteen-month rule because a platform default, a legal hold or a migration reinstates the previous retention period | Account Data | 2 | 2 | 4 | Low | Bill Traynor | 3.2.1, 9.4.7, 12.3.1, 3.1.1
R-25 | A cloud segmentation boundary is changed by a single authorised API call that completes in under a second, with no outage, no symptom and no artefact other than a log entry | Cloud | 3 | 4 | 12 | Moderate | Trevor Kim | 1.2.2, 1.2.8, 10.2.1, 11.4.5, 7.2.2
R-26 | Cloud logging is disabled, diverted, or not monitored for absence, removing the only record that a boundary was changed or a principal acted | Cloud | 2 | 4 | 8 | Moderate | Marcus Hale | 10.2.1, 10.3.2, 10.3.4, 10.5.1, 10.7.2
R-27 | Compromise of the security and administrative services zone yields the identity, patching, endpoint, backup, secrets and privileged-brokering paths into the CDE simultaneously — the concentration cost of routing every crossing through one zone | Network &amp; Segmentation | 3 | 5 | 15 | High | Trevor Kim | 7.2.2, 8.4.2, 1.3.1, 10.2.1, 11.4.5, 6.3.3
R-28 | Automated log review fails silently — a parser breaks, a source stops, a rule stops matching — and a detection gap persists undetected behind a dashboard that still looks healthy | Monitoring &amp; Detection | 3 | 4 | 12 | Moderate | Marcus Hale | 10.4.1, 10.4.1.1, 10.4.2, 10.7.2, 10.7.3
R-29 | A quarterly ASV scan fails and remediation plus rescan is not achieved inside the thirty-day attestation window under obligation C4 | Vulnerability &amp; Change | 3 | 2 | 6 | Low | Owen Castellanos | 11.3.2, 11.3.2.1, 6.3.3, 6.5.1
R-30 | High and critical vulnerabilities are not remediated within one month across the store and appliance estate, because patching 482 sites competes with trading and stops entirely from October to January | Vulnerability &amp; Change | 3 | 4 | 12 | Moderate | Trevor Kim | 6.3.1, 6.3.3, 11.3.1, 11.3.1.1, 6.3.2
R-31 | ‡ Historical account data persists in the call-recording estate and in other unstructured stores, beyond the reach of a forward-only control. Raised on evidence 2026-02-05 under ADR-0005, on the disproof of the assumption that DTMF masking had eliminated spoken account data | Account Data | 4 | 4 | 16 | High | Bill Traynor | 3.2.1, 12.10.7, 9.4.7, 12.3.1, 12.5.2
R-32 | A boundary-affecting change is classified as routine, receives no scope-delta review, no second approver and no re-test obligation, and quietly alters what a zone can reach | Vulnerability &amp; Change | 3 | 4 | 12 | Moderate | Trevor Kim | 1.2.2, 6.5.1, 11.4.5, 12.5.2, 1.2.3
R-33 | Scope creep — a new system, integration, acquisition channel or merchant identifier enters the estate without a scope determination, and the assessed population no longer describes the environment | Governance &amp; People | 3 | 4 | 12 | Moderate | Owen Castellanos | 12.5.1, 12.5.2, 6.5.1, 12.8.1
R-34 | The payment-page script inventory drifts as marketing and analytics tooling is added through a tag manager by people who do not know a payment template from a product page | Payment Channel | 4 | 3 | 12 | Moderate | Sonia Rendell | 6.4.3, 11.6.1, 6.5.1, 12.6.3
R-35 | An application flaw in the storefront exposes order data, tokens or customer records — no PAN, because the iframe holds it, and a customer-facing incident nonetheless | Payment Channel | 3 | 2 | 6 | Low | Sonia Rendell | 6.2.1, 6.2.4, 6.3.2, 6.4.1, 11.3.2
R-36 | Nine vendor-locked POS back-office appliances cannot be authenticated-scanned under constraint CON-03, leaving their vulnerability state unknown on components that are inside the assessed population | Vulnerability &amp; Change | 4 | 4 | 16 | High | Trevor Kim | 11.3.1.2, 6.3.3, 2.2.1, 12.8.5, 11.3.1.1
R-37 | File integrity and change-detection coverage lapses on a CDE component — an agent stops, a baseline is not re-established after a change, an exclusion is widened | Monitoring &amp; Detection | 2 | 3 | 6 | Low | Marcus Hale | 11.5.2, 10.3.4, 10.7.2, 6.5.1
R-38 | Physical access to store stockrooms and network cabinets is not controlled to the standard the network design depends on, so a person with a cable has the access the segmentation model assumes they do not | Physical &amp; Device | 3 | 2 | 6 | Low | Adaeze Nwosu | 9.1.1, 9.2.1, 9.2.2, 9.3.1, 9.5.1
R-39 | Media containing account data — dispute paperwork, signed drafts, retired drives, receipt stock — is disposed of without a certificate of destruction or is held past its retention period | Physical &amp; Device | 2 | 3 | 6 | Low | Adaeze Nwosu | 9.4.5, 9.4.6, 9.4.7, 3.2.1
R-40 | Security awareness completion falls below the charter bar during seasonal onboarding, when the population most likely to encounter a skimmer or a social-engineering attempt is the newest | Governance &amp; People | 2 | 2 | 4 | Low | Owen Castellanos | 12.6.1, 12.6.2, 12.6.3, 12.6.3.1
R-41 | Programme capacity is lost to trading-critical work and a store-side control misses the 2026-09-30 cut-off imposed by the seasonal freeze, leaving it without operating history before QSA fieldwork | Governance &amp; People | 3 | 2 | 6 | Low | Owen Castellanos | 12.1.1, 12.4.1, 12.5.2
R-42 | Evidence produced during the year is not retained in a form the assessor can sample in November — screenshots without dates, reports without populations, attestations without a named attester | Governance &amp; People | 2 | 3 | 6 | Low | Owen Castellanos | 12.5.2, 11.4.1, 10.5.1, 12.1.1
R-43 | Incident response procedures are documented but not exercised against the scenarios this estate actually produces — PAN found where it is not expected, a POI substitution, a rogue access point, a failed segmentation boundary | Governance &amp; People | 2 | 3 | 6 | Low | Marcus Hale | 12.10.1, 12.10.2, 12.10.4, 12.10.5, 12.10.7
R-44 | Time synchronisation drifts or a log source is lost without alerting, degrading the forensic record on which any investigation of the entries above would depend | Monitoring &amp; Detection | 2 | 2 | 4 | Low | Marcus Hale | 10.6.1, 10.6.2, 10.6.3, 10.7.2, 10.5.1

## The 9 High Risks
The 9 High risks — including the two that were RAISED on evidence rather than scored high at the outset
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
ID | Risk | Category | L | I | Score | Rating | Owner | Treating requirement(s)
R-01 | Unauthorised or malicious script executing in the consumer browser on a payment page harvests card data before it reaches the Truvance iframe — PAN never touches a Marketa server and Marketa is still the party that served the page | Payment Channel | 4 | 5 | 20 | High | Sonia Rendell | 6.4.3, 11.6.1, 6.4.1, 6.4.2, 6.5.1, 12.10.1
R-02 | POI device tampering, skimmer overlay or whole-device substitution across 1,914 terminals in 482 buildings that are unattended overnight and staffed by a workforce that turns over seasonally | Physical &amp; Device | 3 | 5 | 15 | High | Adaeze Nwosu | 9.5.1, 9.5.1.1, 9.5.1.2, 9.5.1.3, 12.10.4, 12.6.3
R-05 | A P2PE condition fails at one or more stores — a POI patched into the general data VLAN, an unlisted device, a lapsed solution listing — invalidating the card-present scope reduction that removes 1,914 lanes and 482 servers from the assessed population | Payment Channel | 3 | 5 | 15 | High | Adaeze Nwosu | 12.5.2, 9.5.1.1, 1.3.1, 11.4.5, 12.8.4
R-09 | Third-party service provider concentration — Truvance Payments is hosted checkout, gateway and the single token vault across card-present, e-commerce and MOTO simultaneously; a failure, breach or contractual discontinuity at one provider affects every channel at once | Third Party | 3 | 5 | 15 | High | Owen Castellanos | 12.8.1, 12.8.2, 12.8.3, 12.8.4, 12.8.5, 12.10.1
R-14 | ‡ Segmentation controls in the store estate are not effective, permitting a lower-trust zone to reach a governed zone. Raised on evidence 2026-05-18 under ADR-0005, on the disproof of the assumption that configuration verification across 482 sites establishes segmentation effectiveness | Network &amp; Segmentation | 4 | 4 | 16 | High | Trevor Kim | 11.4.5, 1.2.2, 1.2.8, 1.3.3, 12.5.2
R-17 | Application and system accounts hold embedded, non-rotatable credentials in legacy batch integrations, with interactive use possible and no individual attribution | Identity &amp; Access | 4 | 4 | 16 | High | Trevor Kim | 8.6.1, 8.6.2, 8.6.3, 2.2.2, 8.3.6
R-27 | Compromise of the security and administrative services zone yields the identity, patching, endpoint, backup, secrets and privileged-brokering paths into the CDE simultaneously — the concentration cost of routing every crossing through one zone | Network &amp; Segmentation | 3 | 5 | 15 | High | Trevor Kim | 7.2.2, 8.4.2, 1.3.1, 10.2.1, 11.4.5, 6.3.3
R-31 | ‡ Historical account data persists in the call-recording estate and in other unstructured stores, beyond the reach of a forward-only control. Raised on evidence 2026-02-05 under ADR-0005, on the disproof of the assumption that DTMF masking had eliminated spoken account data | Account Data | 4 | 4 | 16 | High | Bill Traynor | 3.2.1, 12.10.7, 9.4.7, 12.3.1, 12.5.2
R-36 | Nine vendor-locked POS back-office appliances cannot be authenticated-scanned under constraint CON-03, leaving their vulnerability state unknown on components that are inside the assessed population | Vulnerability &amp; Change | 4 | 4 | 16 | High | Trevor Kim | 11.3.1.2, 6.3.3, 2.2.1, 12.8.5, 11.3.1.1

## Distribution
Baseline Distribution and Expected Movement
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Band | Count at baseline | Treatment stance | Expected at close
High (score ≥ 15) | 9 | Treated as a matter of priority; none may remain untreated at programme close | 9 → 0 expected
Moderate (score 8–12) | 21 | Treated on the programme timeline | 21 → 13 expected
Low (score ≤ 6) | 14 | Treated or accepted with a recorded rationale | 14 → 31 expected
Total | 44 | The complete baseline register at 2026-07-15 | 0 High / 13 Moderate / 31 Low at close

## Raised on Evidence
The two risks RAISED on evidence — under ADR-0005, testing that disproves an assumption raises the rating
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
ID | Risk | Score | Movement | What disproved the assumption | What brings it down
R-14 | Store network segmentation is not effective | 4 × 4 = 16 (High) | RAISED 2026-05-18 | SEG-PT-01 — the penetration test proved a store back-office VLAN reachable from guest wireless through a misconfigured trunk. Configuration review had said otherwise | 90 days of clean drift-detection operation. Clock reset to 2026-07-03 after two further divergences; earliest exit 2026-09-30
R-31 | Historical account data persisting in unstructured stores | 4 × 4 = 16 (High) | RAISED 2026-02-05 | PAN-01 — ~11,400 call recordings with audible PAN predating DTMF masking. The control had been implemented forward-only | A second full discovery run returning nothing, due 2026-08-31 — not the cleanup of the first