## Segmentation Test
Segmentation penetration test 2026-05-15 — RESULT: FAIL
Ironwood Security Labs · engagement IWSL-MRG-2026-SEG-01 · fieldwork 2026-05-11 to 05-22 · report 2026-05-29
ID | Severity | Finding | Boundary | Disposition
SEG-PT-01 | Critical | Store back-office VLAN reachable from guest wireless through a misconfigured trunk | B-09 | §5. Remediated estate-wide; re-tested June
SEG-PT-02 | High | Permissive `ROLE-AP` trunk configuration — no allowed-VLAN list — present at 37 stores as a latent precondition | B-09 | Build image corrected to SB-4.2; explicit allowed-VLAN list restored and pushed to all 482 stores; daily assertion added
SEG-PT-03 | High | SNMPv2c read access obtainable from the colleague wireless VLAN at 6 stores, disclosing switch configuration including full VLAN topology and trunk membership — a 1.4.5 internal-topology disclosure and a reconnaissance accelerant | B-06 | Community strings rotated; polling ACL corrected to permit only CT-48 source addresses; exception NSC-EX-01 re-scoped and its review cadence shortened
SEG-PT-04 | Medium | Guest captive portal permitted DNS resolution before terms acceptance, allowing name-based egress from Z7 prior to authorisation | B-09 | Portal walled-garden tightened; DNS restricted to the portal resolver until acceptance
SEG-PT-05 | Medium | Unused switch ports live rather than administratively shut at 9 of 14 tested stores, permitting an unauthenticated device patched into a stockroom port to obtain a VLAN 10 address | Internal to Z5 | Port-state assertion implemented daily across all 482 stores; unused ports shut and assigned to VLAN 999
SEG-PT-06 | Medium | Internal private addressing and infrastructure hostnames disclosed in an unhandled error response from a Z8 storefront service — 1.4.5 | B-13 | Error handling corrected; response inspection added to the edge configuration; retested
SEG-PT-07 | Low | Deprecated cipher suite offered by the management interface of the store WAN edge device on the management VLAN | Z5 management | Cipher configuration hardened in the build image
SEG-PT-08 | Low | Verbose SIP responses from the Austin session border controller disclosing platform and version | B-11 | Response headers suppressed

## Failure Timeline
From configuration confidence to tested boundary — the seven weeks that made the claim mean something
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Date | Event | Significance
2026-03-19 | Design review records segmentation as verified by configuration analysis | Configuration is not proof — this is the assumption the test destroyed
2026-05-11 | Ironwood fieldwork opens across a stratified sample of 14 stores (2.9%) | One stratum deliberately targeted stores with a recent local network change
2026-05-15 | **SEG-PT-01** — store back-office VLAN reached from guest wireless in 19 minutes | Store 0417, Dayton OH
2026-05-15 12:38 | Ironwood notifies Marketa under the rules of engagement | Notification obligation triggered on a Critical finding
2026-05-15 13:19 | Store 0417 isolated — 41 minutes from notification | Containment, not remediation
2026-05-18 | **R-14 raised to 4 × 4 = 16 (High)** under ADR-0005 | The rating expressed a belief that testing disproved
2026-05-19 | Steering Committee extraordinary session | Scope determination provisionally suspended pending remediation
2026-05-19 → 05-20 | Track A — allowed-VLAN list restored at all 37 latent stores | The fast fix
2026-05-20 → 07-06 | Track B — build image SB-4.2 rolled to 482 stores in four waves | The durable fix; 482x rollout is the constraint
2026-05-27 | Cardinal Merchant Bank notified under obligation C7 | No compromise occurred; notified as a matter of transparency
2026-06-15 | Drift-detection control DA-1 to DA-6 live estate-wide | So the next occurrence is found by Marketa, not by a tester
2026-06-22 → 06-26 | Re-test IWSL-MRG-2026-SEG-02 across 41 stores (8.5%) | All 37 latent stores plus 4 Ironwood-selected
**2026-06-26** | **RE-TEST PASSED — zero findings** | Proves the boundary holds today. Does NOT prove the process that let it rot is fixed
2026-07-02 | Cardinal notified of restoration under C7 | Closing the loop on the earlier notification
2026-07-06 | ADR-0006 restored and amended at Steering Committee | Now contingent on the drift control operating, not on a one-off test

## Drift Detection
The control introduced so the next occurrence is found by Marketa — first 31 days of operating history
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 03 · Illustrative Portfolio Sample
Item | Value | Note
DA-1 to DA-6 | Six configuration assertions evaluated continuously across the store estate | Live 2026-06-15
Store-days observed | 14,942 in the first 31 days | —
Divergences detected | 11 at 9 stores | Found by Marketa, not by a tester
**Segmentation-determining divergences** | **2** | Store 1183 (contractor stock switch image, 2026-06-24) and store 0629 (guest SSID moved to local switching, 2026-07-02)
Live path created by either? | **No** — the counterpart precondition was absent in both cases | The fault needs two preconditions to coincide
Effect on the R-14 exit clock | **Reset to 2026-07-03** | Earliest exit 2026-09-30. A clock that never resets is not a clock