## Phase 04 Traceability
What Phase 04 treated, and what it deliberately did not move
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 04 · Illustrative Portfolio Sample
Risk | Baseline | Phase 04 contribution | Standing | Still required | Expected residual
R-01 — unauthorised or malicious script on a payment page | High 20 | 04.10 in full — the 38-script inventory with written justification; named-authoriser workflow with verified conditions; SRI on 27 first-party and 5 third-party scripts; CSP enforcing with nonces, set at the edge as well as the origin; the tag manager removed from all six templates; publication rights cut from 19 accounts to 6; the five-business-day tag approval SLA. Plus 04.07's signed deterministic build and 04.09's edge enforcement of the CSP header | Primary | 11.6.1 monitoring live August 2026 (Phase 06); operating history; self-hosting extended to the remaining vendor-mutable scripts | Moderate
R-34 — payment-page script inventory drift | Moderate 12 | The injection mechanism removed rather than governed; payment-template publication no longer a capability in the tag console; four independent reconciliation mechanisms; SIG-5 brings any template, script, tag or CDN change into significant-change control | Primary | A full cycle of continuous reconciliation with 11.6.1 alongside | Low
R-04 — configuration drift returns faster than assurance detects it | Moderate 12 | CA-1 to CA-6 across 56 Class A components; ≈1.41 million item-assertions; the silence rule; quarterly negative testing of the assertion layer itself | Primary | Sustained coverage through the freeze and into 2027 | Low
R-20 — destructive or extortion malware interrupts trading | Moderate 12 | Anti-malware on all 37 protected components with continuous behavioural analysis; 5.3.3 removable-media scanning; 5.2.3 evaluation of the not-at-risk classes with TRA-5.2.3.1 at six-monthly plus event triggers; tamper-resistant agents under 5.3.5 | Primary | Backup restore testing and the incident-response exercises in Phase 07 | Moderate — structural
R-21 — phishing delivers a foothold used to reach administrative services | Moderate 12 | 5.4.1 automated anti-phishing mechanisms; EDR with tamper protection; the brokered administrative path with no cleartext channel under SCS-11 | Primary | 8.4.2 MFA on all CDE access — Phase 05; 12.6.3 awareness — Phase 07 | Low
R-30 — high and critical vulnerabilities not remediated within one month | Moderate 12 | The 6.3.1 ranking with two hard override rules; the 6.3.3 SLA measured from vendor release; composition-analysis gating that fixes dependencies at build time; the pre-freeze sprint; the `VE-nn` deferral register with a 31 January ceiling; virtual patching at the edge | Primary | Phase 06's 11.3.1 scanning cycle; the freeze itself does not go away | Moderate
R-32 — a boundary-affecting change is classified as routine | Moderate 12 | SIG-4 delegating to the 1.2.2 segmentation-affecting list so the two cannot diverge; mandatory classification not settable by the requester; obligations raised automatically by classification; CA-2 and CA-3 as the backstop that detects the change the process missed | Primary | Sustained classification discipline; the Phase 06 re-test cycle | Low
R-33 — scope creep | Moderate 12 | SIG-1, SIG-6 and SIG-8 make an arrival a significant change; the 6.5.2 confirmation forces the 12.5.2 revisit; acquirer obligation C7 attaches | Primary | Phase 06's 12.5.2 annual confirmation executed against this process | Low
R-35 — an application flaw in the storefront exposes order data or tokens | Low 6 | The 6.2.4 technique set with build-time enforcement; the authorisation test suite; DAST; dependency quarantine and the 6.3.2 inventory; 6.4.2 in blocking mode across all six public-facing applications | Primary | The September application penetration test — Phase 06 | Low
R-37 — file integrity and change-detection coverage lapses on a CDE component | Low 6 | Baseline re-establishment as a change completion criterion rather than a follow-up task; SIG-9 makes the removal or redirection of a detection source a significant change; CA-1's silence rule applied to assertion coverage | Primary | 11.5.2 operation and agent-health monitoring — Phase 06 | Low
R-19 — assets recorded as decommissioned remain powered and reachable | Moderate 9 | CA-1's silence rule; the monthly reconciliation of the assertion population against the 12.5.1 inventory from four sources; decommissioning as a change with a verified end state | Primary | Phase 06's scanning reconciliation | Low
R-29 — an ASV scan fails and the 30-day attestation window is missed | Low 6 | The 7-day Critical SLA on CDE components; the ranking rule making anything internet-exploitable Critical; edge mitigation available within hours to buy the remediation window | Primary | The Phase 06 ASV cycle itself | Low
R-22 — customer-initiated account data by email, web form or special-order note | Moderate 9 | Allow-list input validation and field-level pattern rejection in the storefront and special-order service; the edge rule rejecting Luhn-valid card-shaped values in free-text parameters; the 4.2.2 end-user messaging position | Primary | Awareness and the 12.10.7 procedures — Phase 07 | Low

## Held, Not Reduced
The honest position at the close of Phase 04
Marketa Retail Group — PCI DSS v4.0.1 Program · Phase 04 · Illustrative Portfolio Sample
Item | Position | What changes it
Why several risks are HELD rather than reduced | Every control in this phase was deployed within the last three months. A control with no operating history is a design, not a demonstrated reduction | The register moves when evidence accumulates, not when a control is switched on
R-01 — payment-page script injection | 6.4.3 is fully implemented and three unauthorised scripts were removed. But 6.4.3 is **preventive only**; the detective counterpart 11.6.1 does not land until Phase 06 | Reduces materially once 11.6.1 is operating and both have run a full cycle
The vendor-locked appliances | Nine appliances cannot accept an agent, so baseline compliance is evidenced by observation or vendor attestation rather than by assertion | Becomes **CAP-06** at the assessment; closes only with vendor agreement or replacement
The consistent principle | A baseline document is not a control. The **deployed state** is the control, and measuring it is what makes the claim real | The same lesson Phase 03 learned when a configuration review missed a trunk for eighteen months